## Slide 1
Consulting Services for Embedded Advisors for Electricity Regulatory Commission (ERC) under Electricity Transmission Project (Power Sector Technical Assistance Activity) in Nepal
20th September 2024

## Slide 2: CONTENTS
Sl No | Coverage | Slide No
 | KEY OBJECTIVES & SUPPORT AREAS IDENTIFIED | 3
 | ERC FIVE YEAR ROADMAP | 7
 | STATUS UPDATE ON INCEPTION REPORT | 13
 | ASSOCIATED TASKS AND ACTIVITIES | 18
 | OTHER DISCUSSION POINTS | 49
1
2
3
4
5

## Slide 3: Key Objectives & Support Areas identified

## Slide 4: Key Objectives of the Engagement
Objective 1
Establish ERC as an effective operational stakeholder in Nepal’s power sector through support to develop basic organization processes, staff development and management programs, business and funding arrangements, and necessary tools and logistical support; including a strong data storage and backup system, including ability to disaggregate by key factors such as economic/social groupings.
Objective 2
Support the financial viability of the power sector developing and deploying a consistent, transparent, and robust regulatory system including a clear tariff approval process.
Objective 3
Encourage improved technical performance and electricity service by establishing and monitoring clear technical and customer service standards and linking performance to regulatory outcomes.
Objective 4
Enhance Nepal’s power sector potential through support for policy and regulations that encourages increased competition, more robust sector planning and growth, and effective power trading.
Objective 5
Other Issues and Areas including establishment of an effective public engagement and communication regime, creating and integrating a social equity policy, and clarifying ERC’s mandate while advising the Government on policymaking and sector development.

## Slide 5: Scope of Work – Key Support Areas for ERC
Inputs on Operational Spheres
Providing guidance and direct inputs to regulatory directives in economic, legal, policy and technical spheres
Support in establishing operational practices
Working with ERC staff and Commissioners to establish strong internal decision-making and operational practices
As required, assist coordinating and supporting the tasks of ERC staff;
Review of key documents and submissions
Supporting ERC staff and Commissioners in reviewing key documents and submissions (e.g., tariff applications, power purchase agreements, technical monitoring reports, etc.);
Independent Studies and Strategy Documentation
Supporting ERC in managing independent studies and analyses;
Supporting ERC in development of strategy documents and tools;
Training & Capacity Building
Conducting trainings and other capacity building activities;
Assistance in Power Sector Reform
The Power Sector Reform is an activity under the jurisdiction and purview of the Ministry of Energy, Water Resources and Irrigation, hence this responsibility of the Embedded Advisors shall be limited only to ERC's required functions related to Government initiated Power Sector Reform

## Slide 6: Scope of Work – Major Deliverables
Inception Report
Define objectives, criteria, and work plan.
Assess progress against key goals.
Include initial observations and risks
04
02
03
01
05
Monthly Progress Reports
Review progress against monthly objectives.
Address obstacles, assign actions, and resources.
Include immediate and near-term challenges.
Quarterly Progress Reports
Evaluate longer-term progress and planning.
Jointly agree on next quarter's activities.
Assess lessons learned and corrective actions.
Annual Report
Comprehensive review of annual activities, successes, and challenges.
Update overall project objectives, priorities, and focus areas for the next year.
Analyze progress and propose corrective actions, if required
Final Report
Shall cover all the cumulative issues/activities and deliverables completed

## Slide 7: ERC Five Year Roadmap

## Slide 8: Background - Current Challenges
01
02
03
04
05
06
Delays in receiving approval on financial administration bylaws and employee administration bylaws, thereby limiting the Commission’s technical, administrative, and financial potential.
Lack of adequate workforce affecting management of office for full functioning of the Commission.
Communication gap with respect to apprising Commission's authority, role and responsibility to stakeholders.
Issues in effectively managing regulatory instruments; delay in managing petitions; processing files in a transparent manner.
Limited movement on issues related to power sector reform, open access in the transmission network, wholesale competition, and the determination of T&D (wheeling) charges.
Current limitations in ability to review and amend provisions relating to electricity consumer tariffs, power purchase agreements, pre-approval of public share issuances, etc.
Review of the current situation of the electricity sector including evaluation of past work of the Commission indicates following major gaps/ challenges as per the ERC Five Year Roadmap (2024-25 to 2028-29):

## Slide 9: Key Intended Outcomes of the Roadmap
1
Clear communication of the mission, vision, objectives, and priorities of the Commission to regulators, thereby establishing a consistent regulatory framework
5
2
4
3
Alignment with National Planning Commission's 16th Plan, which focuses on expanding electricity capacity, increasing exports, and boosting domestic energy consumption.
Reduction of regulatory uncertainties to boost investor confidence and promote stability and growth in the energy sector
Platform for gathering feedback from stakeholders, allowing the ERC to address concerns proactively and adjust its strategies to better meet the needs of the sector
Integration of alternative energy sources into the national grid to contribute to the national energy mix
The roadmap aims to outline the regulator's priorities, timelines, and initiatives, providing stakeholders with a transparent plan of upcoming activities with the intent to help manage expectations, align efforts with regulatory goals, and reduce uncertainties. Major intended outcomes are outlined as follows:

## Slide 10: Regulatory Priorities Identified by ERC in Five Year Roadmap (2024-29) (1/2)
As per the draft Five-year Roadmap for ERC (2024-2029) as issued on July 2024, several activities/ targets have already been earmarked based on current needs and challenges
Regulatory priorities Identified
Competition and Consumers’ Rights Protection
  Implementation of Grid code; development of distribution code; Demand forecast, determination of supply energy mix etc
Rate Determination by Licensees
Competition and Consumers’ Rights Protection
Organizational Capacity Development and Corporate Governance
  Tariff framework and reform; Cost of service study; PPA templatization; Determination of T&D wheeling charges; power purchase from Energy storage projects
Coverage
  Open Access directives, Cross Border Energy Trade, Electricity market retail competition model, sustainability study of Community Rural Electricity Entities (CREEs)
  Performance indicators for Generation and Distribution, CAPEX and OPEX benchmarking, Regulatory Accounting Standards, Licensees code of conduct, Project risk mitigations
Dispute Resolution
  Issue Bylaws related to Electricity Regulatory Commission Dispute Resolution

## Slide 11: Regulatory Priorities Identified by ERC in Five Year Roadmap (2024-29) (2/2)
Review of Decision
Providing Policy Suggestions
Investigation and Inspection
Imposition of fines
Determination of Service Charges
Conducting Public Hearing
  Issue Bylaws related to Review of Decision
  Studies on power sector improvement; policy-level suggestions to the GoN; Studies and analyses of prevalent laws ; Clarification of the jurisdiction of the ERC
  Set legal arrangement for immediate investigation and on- site inspection
  Introduce necessary provisions regarding imposition of fines
  Amendment of provision(s) relate to service charges as necessary
  Periodically hold public hearings to address public grievances in all provinces

## Slide 12: ERC Five Year Roadmap Snapshot
KEY TARGETS FOR 2024/25
KEY TARGETS FOR 2026/27
KEY TARGETS FOR 2028/29
Internal Strengthening & Preparatory Works
Dispute Resolution Bylaws
Internal Control System Bylaws
Tariff Studies (Storage Project Tariff, Progressive & Regressive Tariff, Piloting Smart Metering
Tariff Frameworks for Generation & Distribution
Directives to Foster Competition in Power Purchase of Pre-Construction Projects
Directives on Brownfield PPA
Directives on Corporate Governance of Licensees
Review and Monitoring
Stabilization of ERC
STRENGTHENING HUMAN RESOURCE, FINANCIAL RESOURCE,INFRASRUCTURAL RESOURCE AND PLAN
TRANSPARENCY AND ACCOUNTABILITY
STAKEHOLDER CONSULTATION
ADOPTION OF BEST PRACTICES
KEY TARGETS FOR 2025/26
KEY TARGETS FOR 2027/28
Directives on General Network Access and Determination of Wheeling Charges
Cost of Service Study for distribution licensees
Sustainability Study of CREEs
Evidence Generation for Next Stage Reforms
Regulatory Accounting Standards
Distribution Code
Study of wholesale competitive market & retail competition
DIGITAL ARC

## Slide 13: Status Update on Inception Report

## Slide 14: Approach for Inception Report
The activities envisaged under the Objectives have been reviewed along with the ERC five-year Roadmap
In view of the nascent stage of ERC’s operations, focus is primarily on capacity building activities and regulatory frameworks (Directives/Regulations) for operationalization of ERC and ensuring its proper functioning. Activities relating to market structure, IRP, etc. shall be taken up during optional period.
Activities of similar nature have been clubbed in Modules for better clarity
Tasks under each Module have been identified based on RFP and ERC roadmap along with few additional tasks based on discussions
Task under ERC roadmap not forming part of expertise of EAs (i.e. changes in shareholding of licensee, IPO approval, etc.) have not been covered
While undertaking prioritization of key tasks in the first two years, detailed deliberations are being undertaken with the ERC
External experts (under STTA) have been envisaged for few tasks requiring technical knowhow or tasks requiring full-time efforts

## Slide 15: Modules identified based on Scope of Work
Module A
Module B
Module C
Module D
Module E
Module G
Module H
Module F
Implementation of RIMS and DMS
Training and Capacity Building
Development of Bylaws/ Directives/ Rules
Financial Independence and Sustainability
Miscellaneous Activities
Support in Tariff and Other related Activities
Policies and Processes
PPA & Contractual Activities
Identified Modules from SoW

## Slide 16: Inclusions in line with ERC Roadmap
Detailed Mapping of Roadmap Activities with respect to coverage under Scope of Work as per RfP is provided in Annexure
Short-term, Medium-term, and Long-term electricity demand forecast
Prescribe and review necessary instruments of power system operator
Issue the directives on Power Purchase for Energy Storage Project including BESS, Storage Hydropower and Pumped Storage Hydropower.
Install the Citizen’s Charter of Electricity Regulatory Commission
Review the Electricity Consumers’ Rights Protection Directives, 2023
Study of implementation model of retail competition included electricity market
2
1
3
4
5
6
Conduct sustainability study of Community Rural Electricity Entities (CREEs)
7
Note: “++” indicates same has been added in EA work plan over and above Scope of Work covered in the MCA RfP
Issue and implement one or more Directives related to Corporate Governance of Licensees as per necessity
Review the existing Directives on Merger, Acquisition, Takeover, Joining, Purchase/Sale of Licenses, etc.
Set legal arrangement for immediate investigation and on- site inspection
Benchmarking Operating Expenditure of licensees
Study and identify project risk mitigation options
Benchmarking Capital Expenditure of licensees
9
8
10
11
12
13
Introduce necessary provisions regarding imposition of fines
14

## Slide 17: ASSOCIATED TASKS AND ACTIVITIES

## Slide 18: Module A: Financial Independence and Sustainability

## Slide 19: Module A: Financial Independence and Sustainability
3 Months
Support ERC in developing a Policy/Rules for utilization of Funds
Suggestions on inclusions in the draft rules and discussion with Commission
Review and provide comments on draft rules.
Providing support in finalization of the Rules.
Development of annual budget and financial plan to ensure financial independence of ERC
Support ERC and accounts team in estimation of revenue and expenditure
Assess required changes in Fees / Service Charges and help prepare a case for amendment in Act /Rules (if required)
3 Months
Task 1
(RfP Ref No. 2&3)
Task 2
(RfP Ref No. 1)
Sl No | Module & Task Reference | RFP Ref. | Task | Year 1 |  |  |  |  |  |  |  |  |  |  |  | Year 2 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
 |  |  |  | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul
1 | Mod. A, Task 1 | 2&3 | Support in Policy/ Rules for utilization of Funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2 | Mod. A, Task 2 | 1 | Development of annual budget and financial plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Tentative Timeline for Module A

## Slide 20: Module B: Implementation of RIMS and DMS

## Slide 21: Module B: Implementation of RIMS and DMS
9 Months
Need Assessment and onboarding of Implementation partner
Visit to CERC and other SERCs for RIMS/DMS review
Provide support in Deployment of an IT Expert; identify requirements
Support IT expert in gap analysis
Bid process management
Implementation of RIMS and DMS & subsequent support
2(a) Implementation of RIMS and DMS
Oversee Development and Installation
Support in Rollout Strategy and Operational Integration
Provide support in hiring of a dedicated IT support staff
Support during Training and Capacity Building Plan
12 Months
2(b) Post implementation support and guidance
Overview of post implementation support and guidance
12 Months
Requirement of External Support
Task 1
(RfP Ref No. 4)
Task 2
(RfP Ref No. 4)
Tentative Timeline for Module B
Sl No | Module & Task Reference | RFP Ref. | Task | Year 1 |  |  |  |  |  |  |  |  |  |  |  | Year 2 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
 |  |  |  | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul
1 | Mod. B, Task 1 | 4 | Need Assessment and onboarding of Implementation partner |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2 | Mod. B, Task 2a | 4 | Implementation of RIMS and DMS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3 | Mod. B, Task 2b | 4 | Post implementation support | Task to be taken up in Year 3 onwards |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
To be Taken Up in Year 3 onwards

## Slide 22: Module C: Training and Capacity Building

## Slide 23: Module C: Training and Capacity Building (1/3)
10 Days
General Concepts of Power Sector Regulatory Framework (Twice in a Year)
Basics in the theory and practice of economic regulation for licensees; system & market operators, evolution of regulation, market power
Power sector models, types of markets
Basics of Tariff determination Methodology and concepts
Technical Trainings
Technical standards
Basics of T&D, grid planning and operation
System analysis and planning for G,T,D; Merit Order Dispatch
TBD
Functioning of ERC and Rule Making
Communication strategy and processes
Development of rules, practices, processes
PPA, conflict management; Grid code
Technical knowledge for Monitoring & Evaluation
10 Days
Tariff Frameworks and Tariff Setting Methodology
Development of tariff methodologies and the associated processes
Tariff design and evaluation; tariff modeling and analysis.
Regulatory accounting, utility finance & accounting
Consumer behaviour, trends
Theory and practice of performance-based regulation; incentives
Design and implementation of performance incentive mechanisms (PIMs) etc
Requirement of External Support
11 Days
Area 1
Area 2
Area 3
Area 4
2 days of Training program
2 days of Training program
3 days of Training program
Note: Total indicative timeframe includes preparatory work of EAs w.r.t. each topic along with actual training period

## Slide 24: Module C: Training and Capacity Building (2/3)
~45-50 days**
Task-based trainings
Development of a “roadmap” for IPP/PPA regulation
Competitive bidding/procurement process for IPP contracts
Dispute Resolution processes;
Integrated Resource Planning (IRP)
IT system applications etc
Generation related trainings
Hydropower risk assessment and financing.
Project financing as used by IPPs.
Competitive bidding for IPPs.
8 Days
Market Reforms
Inputs on competitive wholesale electricity markets; independent system operators; DAM and RTM; capacity markets; nodal pricing; transmission open access regimes; financial transmission rights; etc.
Inputs on transition roadmap for moving toward wholesale competitive markets
Training on the use of generation and transmission system expansion software.
8 Days
Other Trainings++
Leadership Trainings, Management & Communication
Energy Conservation, Audit, Demand side management, Power Trading
New and emerging areas in power sector - BESS, PSP, Hydrogen, etc.
Requirement of External Support
2 Weeks
Area 5
Area 6
Area 8
Area 7
1 day of Training program
1 day of Training program
~1-2 days for each Training program
**To be firmed up
Note: Total indicative timeframe includes preparatory work of EAs wrt each topic along with actual training period
TBD

## Slide 25: Module C: Training and Capacity Building (3/3)
TBD
Study Tours ++
Tour for building understanding of Power sector and Regulatory Framework (Canada, Norway), interaction with utilities
Tour to India to interact with Regulatory Commissions and observe the functioning of utilities/ power exchange/ LDC, etc.
Tour to countries such as Laos /Brazil for Power Exchange model
Training tours to neighboring countries for knowledge enhancement
Observation tour to understand projects of NEA/BPC, Pvt. IPP, Transmission / Sub-station projects, load Dispatch Center
On the Job Training
Inputs on multiple topics/ tasks in line with coverage of SoW as and when required during course of engagement
Continual
Requirement of External Support
Area 9
Area 11
Note: Total indicative timeframe includes preparatory work of EAs wrt each topic along with actual training period
Workshop/ Lectures
Prominent Scholars, practitioners and industry expert to share ideas/research on regulatory aspects including new technologies
Quarterly
Area 10

## Slide 26: Module C: Tentative Timeline
Sl No | Module & Task Reference | RFP Ref. | Task/ Training | Year 1 |  |  |  |  |  |  |  |  |  |  |  | Year 2 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
 |  |  |  | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul
1 | Mod. C, Task 11 | C11 | On the Job Training++ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2 | Mod. C, Task 9 | C9 | Study Tours++ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3 | Mod. C, Topic 1 | C1 | General Concepts - Regulatory Framework |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4 | Mod. C, Topic 3 | C5 | Functioning of ERC and Rule Making |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
5 | Mod. C, Topic 4 | C2 | Tariff Frameworks and Tariff Setting Methodology |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
6 | Mod. C, Topic 2 | C3 | Technical Trainings |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
7 | Mod. C, Topic 5 | C4 | Task-based trainings | To be Discussed and Finalized |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
8 | Mod. C, Topic 6 | C6 | Generation related trainings |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
9 | Mod. C, Topic 7 | C7 | Market Reforms |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
10 | Mod. C, Topic 8 | C8 | Other Trainings++ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 27: Module D: Development of Bylaws/ Directives/ Rules

## Slide 28: Module D: Development of Bylaws/ Directives/ Rules (1/4)
4 Months
Support in finalization of Internal Control System Bylaws
Review of draft of Internal Control System bylaws and suggest changes
Support in finalization of draft for circulation for public consultation
Review of stakeholder comments and finalization
Adopt procedural rules & substantive rules including rules of practice & procedure and an operationalized three-tier decision-making process
Review support w.r.t procedures and practices; benchmarking study
Support in draft preparation for Coduct of Business / SOP Directives
Review of stakeholder comments and
Support in finalization of Rules/ Directive
5 Months
Develop and/or update a Tariff Methodology, filing requirements & transparent/robust review guidelines. Develop costing & pricing bylaws/directives & guidance on uniform chart of accounts.
Support in appointment of Tariff Expert
Interaction with the Consultant on the framework of Tariff determination
Preparation of concept paper
support in framing Tariff directives
Workshop arrangement
16 Months
Directives on Appointment of Consultant
Support in identification of key provisions for Appointment of Consultant
Support in Preparation & finalization of Directive
Requirement of External Support
7 Months
Task 1
(++)
Task 2
(RfP Ref No. 8)
Task 3
(RfP Ref No. 13)
Task 4
(++)
Note: “++” denotes additional inclusion beyond mentioned scope in RfP

## Slide 29: Module D: Development of Bylaws/ Directives/ Rules (2/4)
8 Months
Grievance Redressal Bylaws
Support ERC Staff in Study the existing provisions and process for grievance redressal
Support in Stakeholder consultation of the various options
Support in preparation and finalization of related bylaws
Generation Tariff Directive/ Framework for Alternate Energy Sources (other than Hydro) - including BESS, Storage, PSP, Wind, etc.
Support in appointment of Consultant
Support to ERC in reviewing Consultant's study
Support in preparation and finalization of draft generation tariff framework, directive
14 Months
Directive on Standard of Performance Regulations
Support ERC Staff in identification of key standard of performance parameters
Support in preparation and finalization of Directives on SOP
8 Months
Develop rules & framework for open-access regime for transmission network & support transition process
Support ERC in preparation of concept note and undertaking efforts for operationalization of open access
Engagement of Consultant
Support ERC in undertaking a detailed review of Open Access framework and identify necessary changes
Support in preparation and finalization of open access framework
Requirement of External Support
15 Months
Task 5
(++)
Task 6
(++)
Task 7
(++)
Task 8
(RfP Ref No 24)
Majority of activities to be taken Up in Year 3 onwards
Note: “++” denotes additional inclusion beyond mentioned scope in RfP

## Slide 30: Module D: Development of Bylaws/ Directives/ Rules (3/4)
TBD
Establish market rules/regulations regarding scheduling, dispatch and settlement
Support in appointment of technical consultant
Review and provide feedback on the study and draft rules/regulations
Support during stakeholder consultation and finalization of rules
Directives/rules on IRP / system analysis and planning for GTD
Support in appointment of Consultant
Support in reviewing Consultant's study
Providing comments on draft Directives/ Rules
Stakeholder consultation support and support in finalization of Directives/ Rules
TBD
Develop and/or update rules & directives on integration of energy efficiency & demand response into sector planning
Support ERC staff in preparing draft rules/ directives for energy effiiciency and demand response
Review of stakeholder comments and support in finalization of Rules/ Directive
TBD
Requirement of External Support
Task 9
(RfP Ref No. 17)
Task 10
(RfP Ref No. 22)
Task 11
(RfP Ref No. 23)
To be Taken Up in Year 3 onwards
To be Taken Up in Year 3 onwards
To be Taken Up in Year 3 onwards

## Slide 31: Module D: Development of Bylaws/ Directives/ Rules (4/4)
Review of Electricity Consumer's Rights Protection Directives 2023
Support in identification of key provisions for revision
Support in preparation and finalization of amendments
Requirement of External Support
TBD
Task 12
(++)
To be Taken Up in Year 3 onwards
ERC develops & implements regulations on power trading (regional & domestic)
Support in appointment of Consultant
Support in preparation of concept note
support to ERC in issuance of Policy document for CBT
Support in preparation and finalization of Rules/ Directives
TBD
Task 13
(RfP Ref No. 27)
To be Taken Up in Year 3 onwards
Note: “++” denotes additional inclusion beyond mentioned scope in RfP

## Slide 32: Module D: Tentative Timeline (1/2)
Sl No | Module & Task Reference | RFP Ref. | Task | Year 1 |  |  |  |  |  |  |  |  |  |  |  | Year 2 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
 |  |  |  | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul
1 | Mod. D, Task 1 | ++ | Finalization of Internal Control System Bylaws |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2 | Mod. D, Task 8a | 24 | Support in preparation of concept note and efforts for open access |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3 | Mod. D, Task 3 | 13 | Tariff methodology, filing requirements & transparent/robust review guidelines; Costing & pricing bylaws/directives; uniform chart of accounts. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4 | Mod. D, Task 2 | 8 | Adopt procedural rules & substantive rules; 3-tier decision-making process |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
5 | Mod. D, Task 4 | ++ | Directives on Appointment of Consultant |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
6 | Mod. D, Task 5 | ++ | Grievance Redressal Bylaws |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
7 | Mod. D, Task 6 | ++ | Generation Tariff Directive/ Framework for Alternate Energy Sources |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 33: Module D: Tentative Timeline (2/2)
Sl No | Module & Task Reference | RFP Ref. | Task | Year 1 |  |  |  |  |  |  |  |  |  |  |  | Year 2 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
 |  |  |  | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul
8 | Mod. D, Task 7 | ++ | Directive on Standard of Performance Regulations (covered in Misc.) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
9 | Mod. D, Task 8b | 24 | Develop rules & framework for open-access wrt transmission | Task to be taken up in Year 3 onwards |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
10 | Mod. D, Task 9 | 17 | Market rules/regulations for scheduling, dispatch and settlement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
11 | Mod. D, Task 10 | 22 | Directives/rules on IRP / system analysis and planning for GTD Oversee development & consultations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
12 | Mod. D, Task 11 | 23 | Directives on integration of energy efficiency & demand response into sector planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
13 | Mod. D, Task 12 | ++ | Review of Electricity Consumer's Rights Protection Directives 2023 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
14 | Mod. D, Task 13 | 27 | Regulations on power trading (regional & domestic) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 34: Module E: Support in Tariff and Other related Activities

## Slide 35: Module E: Support in Tariff and Other related Activities (1/3)
4 Months
Conduct transparent, efficient tariff review process & approval of initial tariff application; Implement in-period reporting & adjustment processes
Support to ERC Staff in Initial Scrutiny of Tariff Petition,
Support ERC in prudence check of ARR components
Support in public consultation and tariff order issuance
Support in Generic Tariff determination for Alternate Sources of Energy
Support in appointment of Consultant
Support in benchmarking and tariff determination exercise
Support in public consultation and finalization of Order for generic tariff
7 Months
Engage with NEA for preparation of Regulatory Accounts
Interacting with NEA officials periodically for preparation of Regulatory Accounts and other procedures
Supporting ERC in handholding NEA officials
Review of progress and provide necessary support to NEA/Consultant
4 Months
Support in review of Transmission Tariff and Charges
Support to ERC Staff in Initial Scrutiny of Tariff Petition,
Support ERC in prudence check of ARR components
Support in public consultation and tariff order issuance
Requirement of External Support
4 Months
Task 1
(RfP Ref No. 15)
Task 2
(++)
Task 3
(RfP Ref No. 14)
Task 4
(++)
Note: “++” denotes additional inclusion beyond mentioned scope in RfP

## Slide 36: Module E: Support in Tariff and Other related Activities (2/3)
3 Months
Engage with NEA for tariff application preparation
Undertake a workshop for providing guidance of requirements of Tariff Regulations and formats
Continual doubt clarification as and when required
Engage with NEA for undertaking a Cost-of-service (CoS) Study
Review of existing approaches to CoS
Drafting and finalization of a Concept paper for undertaking CoS Model
Support to ERC in coordinating with NEA on the CoS study
Support ERC in review of findings
TBD
Support in review of Tariff for new HEPs (selling power to Distribution Licensees)
Support to ERC Staff in Initial Scrutiny of Tariff Petition,
Support ERC in prudence check of ARR components
Support in public consultation and tariff order issuance
TBD
Forecasting with respect to demand-supply over long-term, medium-term and short-term under IRP Directives
Support to ERC Staff in Initial Scrutiny
Support ERC in analysis and prudence check of submitted information
Support in public consultation and order issuance
Requirement of External Support
TBD
Task 5
(RfP Ref No. 14)
Task 6
(RfP Ref No. 14)
Task 7
(++)
Task 8
(++)
To be Taken Up in Year 3 onwards
To be Taken Up in Year 3 onwards
To be Taken Up in Year 3 onwards
Note: “++” denotes additional inclusion beyond mentioned scope in RfP

## Slide 37: Module E: Support in Tariff and Other related Activities (3/3)
Requirement of External Support
Study for Tariff Reforms
Support in appointment of Consultant
Support to ERC / Consultant in analyzing the data from the Study
Preparation of Approach Paper w.r.t. Tariff Schedule
Stakeholder/ Public consultation support
Review of comments of stakeholders and Inclusion in Tariff Order
TBD
Task 9
(++)
To be Taken Up in Year 3 onwards
Note: “++” denotes additional inclusion beyond mentioned scope in RfP
Sl No | Module & Task Reference | RFP Ref | Task | Year 1 |  |  |  |  |  |  |  |  |  |  |  | Year 2 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
 |  |  |  | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul
1 | Mod. E, Task 1 | 15 | Conduct transparent, efficient tariff review process & approval; in-period reporting & adjustment processes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2 | Mod. E, Task 2 | ++ | Support in Generic Tariff determination for Alternate Sources of Energy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3 | Mod. E, Task 3 | 14 | Engage with NEA for preparation of Regulatory Accounts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4 | Mod. E, Task 4 | ++ | Support in review of Transmission Tariff and Charges |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
5 | Mod. E, Task 5 | 14 | Engage with NEA for tariff application preparation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
6 | Mod. E, Task 6 | 14 | Engage with NEA for undertaking a Cost-of-service Study | Task to be taken up in Year 3 onwards |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
7 | Mod. E, Task 7 | ++ | Support in review of Tariff for new HEPs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
8 | Mod. E, Task 8 | ++ | Forecasting with respect to demand-supply |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
9 | Mod. E, Task 9 | ++ | Study for Tariff Reforms |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 38: Module F: Policies and Process

## Slide 39: Module F: Policies and Process (1/2)
10 Months
ERC to initiate & lead process (with NEA & IPPs) for development of updated Grid Code
Support in appointment of consultant for preparation of Grid Code (GC)
Support in assessing Consultant's study including identification of changes in GC
Support in stakeholder consultation and finalization of GC
Develop & implement public engagement & consultation policies & processes
Support Commission in identifying the key strategies for public engagement and consultation
Provide support from time-to-time during strategy implementation
As required
Distribution and Supply Code
Support in appointment of consultant for preparation of Distribution & Supply Code
Support in assessing Consultant's study including identification of changes
Support in stakeholder consultation and finalization of GC Distribution & Supply Code
11 Months
Establish information filing requirements for power sector stakeholders
Support ERC staff in identification of key parameters for G, T and D business
Support ERC staff in preparation of specific guidelines and formats
Support ERC in regular monitoring and reporting by the licensees
Requirement of External Support
TBD
Task 1
(RfP Ref No. 20)
Task 2
(RfP Ref No. 11)
Task 3
(++)
Task 4
(RfP Ref No. 21)
Note: “++” denotes additional inclusion beyond mentioned scope in RfP

## Slide 40: Module F: Policies and Process (2/2)
Develop system for conducting electronic hearings (E-Court) and other proceedings and infrastructure for acquisition of E- Conference facilities
Hiring of IT Expert for facilitating need assessment of IT hardware and software required for conducting of E-court
Support ERC in inclusion of provisions for E-court hearing in respective Directive/Rules
ERC engages in or leads policy and planning processes associated with market restructuring, including unbundling of distribution utility
Appointment of Consultant for Power Sector Reforms
Provide support in preparation of Approach Paper
Support in discussion and presentations with key stakeholders
Support in preparation of Policy paper with respect to market reforms and unbundling
Support in key activities required for furthering the process of market restructuring and reforms
TBD
Requirement of External Support
Task 5
(RfP Ref No. 10)
Task 6
(RfP Ref No. 28)
To be Taken Up in Year 3 onwards
TBD
To be Taken Up in Year 3 onwards

## Slide 41: Module F: Tentative Timeline
Sl No | Module & Task Reference | RFP Ref. | Task | Year 1 |  |  |  |  |  |  |  |  |  |  |  | Year 2 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
 |  |  |  | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul
1 | Mod. F, Task 1 | 20 | Development of updated Grid Code and Standards |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2 | Mod. F, Task 2 | 11 | Develop & implement public engagement & consultation policies & processes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3 | Mod. F, Task 3 | ++ | Distribution and Supply Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4 | Mod. F, Task 5 | 10 | Develop system for conducting electronic hearings (E-Court) and other proceedings; E- Conference facilities | Task to be taken up in Year 3 onwards |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
5 | Mod. F, Task 6 | 28 | Policy and planning processes wrt market restructuring, including unbundling of distribution utility [Wholesale Competitive Market, Retail Competition, Power Exchange] |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
6 | Mod. F, Task 4 | 21 | Establish information filing requirements for power sector stakeholders, monitoring & reporting regime | To be Finalized |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 42: Module G: PPA & Contractual Activities

## Slide 43: Module G: PPA & Contractual Activities
4 Months
Review of new PPAs with Distribution Licensee (Ongoing review & approval of PPAs and new projects)
Support in review of the Petition
Support during stakeholder consultation
Support in analysis and preparation of Order
Populate database of cost information on generation plants in Nepal & contribute to development of ERC IPP Roadmap guiding effective regulation of IPPs
Concept Paper preparation support (covering greenfield and brownfield projects)
Preparation of draft guidelines/ policy
Support in public consultation
7 Months
Preparation of Guidelines / Standard PPA (Ongoing review & approval of PPAs and new projects)
Support in appointment of Consultant
Support in benchmarking studies
Stakeholder consultation support
10 Months
Initiate & lead consultations & planning on transition to a competitive bidding process for new power projects. Develop IPP Roadmap for effective regulation of IPPs
Concept paper development support
Support in consultant appointment
Support in framing policy paper and bid documents
Requirement of External Support
8 Months
Task 1
(RfP Ref No. 18)
Task 2
(RfP Ref No. 16)
Task 3
(RfP Ref No. 18)
Task 4
(RfP Ref No. 26)

## Slide 44: Module G: Tentative Timeline
Sl No | Module & Task Reference | RFP Ref | Task | Year 1 |  |  |  |  |  |  |  |  |  |  |  | Year 2 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
 |  |  |  | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul
1 | Mod. G, Task 1 | 18 | Review of new PPAs with Distribution Licensee |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2 | Mod. G, Task 2 | 16 | Database of cost information on generation plants in Nepal & contribute to ERC IPP Roadmap |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3 | Mod. G, Task 3 | 18 | Preparation of Guidelines / Standard PPA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4 | Mod. G, Task 4 | 26 | Initiate & lead consultations & planning on transition to a competitive bidding process for new power projects. Develop IPP Roadmap for effective regulation of IPPs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 45: Module H: Miscellaneous Tasks & Activities

## Slide 46: Module H: Miscellaneous Tasks & Activities
As Required
Clarifying ERC’s mandate in the power sector and advising the Government on policymaking and power sector development.
Activities as per requirement basis discussions with ERC
Study on Social Tariff setting
Support in appointment of Consultant
Provide inputs to Consultant / ERC during the study
Support to ERC / Consultant in analyzing the data
Support in public consultation and finalization of revised tariff schedule in alignment with the findings of the study
TBD
Support in Review of Citizen's Charter
Support ERC in preparation of draft of Citizen Charter
Support ERC in finalization
Requirement of External Support
Task 1
(RfP Ref No. 31)
Task 2
(RfP Ref No. 30)
Task 3
(++)
To be Taken Up in Year 3 onwards
TBD
To be Taken Up in Year 3 onwards
Note: “++” denotes additional inclusion beyond mentioned scope in RfP

## Slide 47: Module H: Tentative Timeline
Sl No | Module & Task Reference | RFP Ref. | Task | Year 1 |  |  |  |  |  |  |  |  |  |  |  | Year 2 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
 |  |  |  | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul
1 | Mod. H, Task 1 | 31 | Creating and integrating a social equity policy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2 | Mod. H, Task 2 | 30 | Study on Social Tariff setting | Task to be taken up in Year 3 onwards |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3 | Mod. H, Task 3 | ++ | Support in Review of Citizen's Charter |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 48: OTHER DISCUSSION POINTS

## Slide 49: Way Forward and few Discussion Points
Finalize Inception Report based on stakeholders inputs
Additional support to ERC is crucial for implementation of Roadmap
  Contract of four (4) resources deployed under DOS support ends in October 24
  Anticipated delays in recruitment / deployment of regular staff
Leverage Short-term Technical Advisors for specific tasks identified in workplan
Overcome infrastructure related issues which ERC might face in short-term

## Slide 50
Deloitte refers to one or more of Deloitte Touche Tohmatsu Limited, a UK private company limited by guarantee (“DTTL”), its network of member firms, and their related entities. DTTL and each of its member firms are legally separate and independent entities. DTTL (also referred to as “Deloitte Global”) does not provide services to clients. Please see www.deloitte.com/about for a more detailed description of DTTL and its member firms.
This material has been prepared by Deloitte Touche Tohmatsu India LLP (“DTTILLP”), a member of Deloitte Touche Tohmatsu Limited, on a specific request from you and contains proprietary and confidential information. This material may contain information sourced from publicly available information or other third party sources. DTTILLP does not independently verify any such sources and is not responsible for any loss whatsoever caused due to reliance placed on information sourced from such sources. The information contained in this material is intended solely for you. Any disclosure, copying or further distribution of this material or its contents is strictly prohibited.
Nothing in this material creates any contractual relationship between DTTILLP and you. Any mutually binding legal obligations or rights may only be created between you and DTTILLP upon execution of a legally binding contract. By using this material and any information contained in it, the user accepts this entire notice and terms of use.
©2024 Deloitte Touche Tohmatsu India LLP. Member of Deloitte Touche Tohmatsu Limited
Deloitte Touche Tohmatsu India Private Limited (U74140MH199 5PTC093339), a private company limited by shares, was converted into Deloitte Touche Tohmatsu India LLP, a limited liability partnership (LLP Identification No. AAE-8458), with effect from October 1, 2015.

## Slide 51: Scope of Work – Detailed support areas and time allocation
Support in establishing core regulatory documentation & Process
Support development of core regulatory documents and processes for adoption by ERC and, as necessary, distribution to power sector stakeholders.
Advisors can expect to support definition of requirements, options analysis, development of draft documents, stakeholder consultation, and development of final documents.
Where external consultants are engaged by MCA-Nepal to develop specific regulatory tools, the Advisors may be required to support this process through contributions to the development of terms of reference or other inputs and then to support ERC in engaging with the external consultants during execution of those assignments.
Advise on sector issues from regulatory aspect
Performing services as a regulatory expert through direct analysis or engagement on issues of regulatory substance relevant to the expertise of the Advisors.
In this role, the Advisors would function essentially as core technical staff for the ERC in order to support effective execution of the Commission’s duties.
Depending on the ERC’s progress in hiring senior technical staff members, the Advisors may be asked to coordinate and manage the work of the less-senior ERC staff.
Training and capacity building of ERC Staff
Developing and performing structured training or capacity building sessions for ERC staff and Commissioners.
The Advisors will be responsible for identifying priority capacity and knowledge areas, assessing staff in those areas, developing training materials and modules, and delivering training in a structured manner (e.g., classroom training).
Mentoring ERC Staff and Commissioners
Mentoring or on-the-job training for ERC staff and Commissioners.
In this capacity, rather than acting as resources for conducting specific regulatory work, the Advisors will support ERC staff and Commissioners and provide guidance as they conduct their own work.
Thought Leadership and Advisory Support for Sector Reform
Supporting thought leadership and advisory support on power sector reform and development in Nepal.
The Advisors, in coordination with ERC staff and Commissioners, will identify strategic or priority issues needed to help Nepal’s power sector achieve expected goals over the next several years and develop white papers, consultative strategies, or other measures to help advance these causes.
Expected time to be devoted
25%
30%
25%
15%
5%

## Slide 52: Deliverables – Year 1
Activity | Tentative Timeline
Develop a realistic and adequate budget; identify funding requirements & prepare/execute regulatory directives to meet those needs; create ERC Fund Management Policy | By Mid-2024
ERC achieves self-funding objectives to increase financial independence from the GoN through regulatory levies/fees, etc. | 2024
Purchase administrative & logistical support (e.g., computers, printers, etc.) necessary for immediate ERC operation | By early-2025
Purchase & installation of Regulatory Information Management System (RIMS) and Docket Management System (DMS), with link to the ERC website. | By late 2025
ERC to establish & implement onboarding program and performance management plan for new staff | By 2025 Ongoing
Provide basic substantive training to new staff in areas including regulatory theory & practice; basics of regulatory accounting & finance; technical operations & management in the power sector | 2025-2026
Develop skills and knowledge for Commission members and senior staff through day-to-day mentoring, study tours, technical short-courses, and international regulatory exchanges | 2024-2027
ERC has adopted procedural rules & substantive rules including rules of practice & procedure and an operationalized three-tier decision-making process | 2024-2025
ERC installs & implements Regulatory Information Management System and Docket Management System, with links to the ERC website | 2025-2027
ERC to develop system for conducting electronic hearings (E-Court) and other proceedings and infrastructure for acquisition of E-Conference facilities | 2025-2027
Develop & implement public engagement & consultation policies & processes to ensure regular, transparent communication with power stakeholders & the general public | Early 2025-2026

## Slide 53: Deliverables – Year 2
Activity | Tentative Timeline
Develop and/or update knowledge & capacity of ERC staff in key areas including elements of a tariff submission, embedded & marginal cost theories; tariff modeling & analysis; IPP project financing; utility accounting, etc. | By late 2025- 2026
Develop and/or update a tariff methodology, filing requirements & transparent/robust review guidelines. Develop costing & pricing by- laws/directives & guidance on uniform chart of accounts | By late 2024- 2025
Engage with NEA during update of regulatory accounts, cost-of-service analysis, tariff application preparation | By late 2024- 2025
Conduct transparent, efficient tariff review process & approval of initial tariff application, including transparent stakeholder involvement. Implement in-period reporting & adjustment processes | By early 2025
Create and begin populating database of cost information on generation plants in Nepal & contribute to development of ERC IPP Roadmap guiding effective regulation of IPPs | 2025-2026
Establish market rules/regulations regarding scheduling, dispatch and settlement in line with efficient system operation to reduce costs of supply | 2025-2027
Ongoing review & approval of PPAs and new projects | Ongoing

## Slide 54: Detailed Mapping with respect to coverage of Roadmap Vs. Engagement (1/7)
Ref No | Commission’s Activities as outlined in ERC Roadmap | Mapping in RfP | Coverage in MCA RfP
4.2.1 | Technical Management |  | 
1 | Implement Nepal Electricity Grid Code, 2023 and review as necessary | 20 | ERC to initiate & lead process (with NEA & IPPs) for development of updated Grid Code including planning requirements, connection requirements, metering, technical standards,
2 | Prepare and implement Distribution Code | 20a | Supporting ERC to develop specifications and hire consultants to develop and/or update technical standards and codes (e.g., Grid Code, Planning Code, Distribution Code) or to develop these requirements in-house.
3 | Prescribe and review necessary instruments prescribing the responsibilities of power system operator |  | Not Covered
4 | Conduct Short-term, Medium-term, and Long-term electricity demand forecast and update it accordingly |  | Not Covered
5 | Conduct a study to determine the supply electricity mix of electricity to be purchased by the distribution licensees | 22e | Support ERC to establish and enable a system analysis and planning for the generation, transmission and distribution process in Nepal’s power sector.
6 | Prepare and implement a plan to purchase the required electricity at the lowest possible cost by distribution licensees | 22e | Support ERC to establish and enable a system analysis and planning for the generation, transmission and distribution process in Nepal’s power sector.
4.2.2 | Rate Determination by Licensees |  | 
7 | Conduct necessary studies oriented towards tariff reform | 13 | Develop and/or update a tariff methodology, filing requirements & transparent/robust review guidelines. Develop costing & pricing bylaws/directives & guidance on uniform chart of accounts
BACK TO MAIN SLIDE

## Slide 55: Detailed Mapping with respect to coverage of Roadmap Vs. Engagement (2/7)
Ref No | Commission’s Activities as outlined in ERC Roadmap | Mapping in RfP | Coverage in MCA RfP
4.2.2 | Rate Determination by Licensees |  | 
8 | Conduct cost of service studies for distribution licensees | 14 | Engage with NEA during update of regulatory accounts, cost-of-service analysis, tariff application preparation
9 | Prepare and implement a comprehensive consumer tariff framework | 13 | Develop and/or update a tariff methodology, filing requirements & transparent/robust review guidelines. Develop costing & pricing bylaws/directives & guidance on uniform chart of accounts
10 | Prepare and implement the template of Power Purchase Agreement | 18 | Ongoing review & approval of PPAs and new projects
11 | Prepare and implement new directives to foster competition in power purchase of pre-construction projects | 18 | Ongoing review & approval of PPAs and new projects
12 | Prepare and implement directives related to the second stage of power purchase agreements | 18 | Ongoing review & approval of PPAs and new projects
13 | Prepare and implement the directives on Determination of Transmission and Distribution Wheeling Charge | 12b | Develop and conduct training in advanced regulatory knowledge and skills such as utility accounting and finance, cost of capital, cash management, project financing, wheeling and transmission tariffs, and performance-based regulation, among other topics.
14 | Issue the directives on Power Purchase for Energy Storage Project including BESS, Storage Hydropower and Pumped Storage Hydropower. |  | Not Covered
BACK TO MAIN SLIDE

## Slide 56: Detailed Mapping with respect to coverage of Roadmap Vs. Engagement (3/7)
Ref No | Commission’s Activities as outlined in ERC Roadmap | Mapping in RfP | Coverage in MCA RfP
4.2.3 | Competition and Consumers’ Rights Protection |  | 
15 | Issue Open Access Directives to Transmission Network | 24 | Develop rules & framework for open-access regime for transmission network & support transition process
16 | Issue Directives related to Cross-border Electricity Trade | 27a | Support ERC to develop policy, regulatory reform, tariff model including legal & regulatory framework for electricity market development, regional power pools and cross border power trading.
17 | Install the Citizen’s Charter of Electricity Regulatory Commission |  | Not Covered
18 | Review the Electricity Consumers’ Rights Protection Directives, 2023 |  | Not Covered
19 | Study of relevance and implementation model of Wholesale Competitive Market | 25e | Conduct advanced training in areas such as dispute resolution, contract management, competitive wholesale markets rules and oversight, competitive bidding for IPP contracts.
20 | Study of implementation model of retail competition included electricity market |  | Not Covered
21 | Issue Directives related to conditions to be followed by the trade licensees | 27 | ERC develops & implements regulations on power trading (regional & domestic)
22 | Conduct sustainability study of Community Rural Electricity Entities (CREEs) |  | Not Covered
BACK TO MAIN SLIDE

## Slide 57: Detailed Mapping with respect to coverage of Roadmap Vs. Engagement (4/7)
Ref No | Commission’s Activities as outlined in ERC Roadmap | Mapping in RfP | Coverage in MCA RfP
4.2.4 | Organizational Capacity Development and Corporate Governance |  | 
23 | Benchmarking Operating Expenditure of licensees |  | Not Covered
24 | Benchmarking Capital Expenditure of licensees |  | Not Covered
25 | Measuring key performance indicators of distribution licensees | 21a | Support development of a monitoring regime for Nepal’s power sector including developing key performance indicators and benchmarks related to technical performance and quality of service. Identify, as needed, tools, equipment, and processes for performing regulatory oversight of technical measures (e.g., site visits), and support ERC in reviewing submissions by regulated entities.
26 | Measuring key performance indicators of generation licensees | 21a | Support development of a monitoring regime for Nepal’s power sector including developing key performance indicators and benchmarks related to technical performance and quality of service. Identify, as needed, tools, equipment, and processes for performing regulatory oversight of technical measures (e.g., site visits), and support ERC in reviewing submissions by regulated entities.
27 | Issue and implement one or more Directives related to Corporate Governance of Licensees as per necessity |  | Not Covered
28 | Review the existing Directives on Merger, Acquisition, Takeover, Joining, Purchase/Sale of Licenses, etc. |  | Not Covered
BACK TO MAIN SLIDE

## Slide 58: Detailed Mapping with respect to coverage of Roadmap Vs. Engagement (5/7)
Ref No | Commission’s Activities as outlined in ERC Roadmap | Mapping in RfP | Coverage in MCA RfP
4.2.4 | Organizational Capacity Development and Corporate Governance |  | 
29 | Prepare and implement workplan on expansion, diversification, and promotions of electricity market. | 27a | Support ERC to develop policy, regulatory reform, tariff model including legal & regulatory framework for electricity market development, regional power pools and cross border power trading.
30 | Prepare and implement Regulatory Accounting Standards | 6 | Provide basic substantive training to new staff in areas including regulatory theory & practice; basics of regulatory accounting & finance; technical operations & management
31 | Prepare and implement code of conduct for licensees to protect the interests of general shareholders | 25a | Support ERC in developing substantive regulatory tools and directives on issues including PPA reviews, IPOs/share issuances, dispute resolution, codes of conducts for licenses in Nepal’s power sector, etc.
32 | Study and identify project risk mitigation options |  | Not Covered
4.2.5 | Dispute Resolution |  | 
33 | Issue Bylaws related to Electricity Regulatory Commission Dispute Resolution | 25 | Develop knowledge & capacity of ERC staff in key areas including dispute resolution, competitive bidding for power projects, power sector models, restructuring of power sector
4.2.6 | Review of Decision |  | 
34 | Issue Bylaws related to Review of Decision | 13 | Develop and/or update a tariff methodology, filing requirements & transparent/robust review guidelines. Develop costing & pricing bylaws/directives & guidance on uniform chart of accounts
BACK TO MAIN SLIDE

## Slide 59: Detailed Mapping with respect to coverage of Roadmap Vs. Engagement (6/7)
Ref No | Commission’s Activities as outlined in ERC Roadmap | Mapping in RfP | Coverage in MCA RfP
4.2.7 | Providing Policy Suggestions |  | 
35 | Provide suggestions on matters requested by the GoN | 31 | Clarifying ERC’s mandate in the power sector and advising the Government on policymaking and power sector development.
36 | Conduct studies on power sector improvement and provide policy-level suggestions to the GoN. | 31 | Clarifying ERC’s mandate in the power sector and advising the Government on policymaking and power sector development.
37 | Conduct studies and analyses of prevalent laws in order to clarify the jurisdiction of the Electricity Regulatory Commission and provide policy-level suggestions to the GoN. | 31 | Clarifying ERC’s mandate in the power sector and advising the Government on policymaking and power sector development.
38 | Provide policy-level suggestions to the GoN on handover of electricity projects to the GoN post-generation license period. | 31 | Clarifying ERC’s mandate in the power sector and advising the Government on policymaking and power sector development.
4.2.8 | Investigation and Inspection |  | 
39 | Set legal arrangement for immediate investigation and on- site inspection |  | Not Covered
4.2.9 | Imposing Fines |  | 
40 | Introduce necessary provisions regarding imposition of fines |  | Not Covered
BACK TO MAIN SLIDE

## Slide 60: Detailed Mapping with respect to coverage of Roadmap Vs. Engagement (7/7)
Ref No | Commission’s Activities as outlined in ERC Roadmap | Mapping in RfP | Coverage in MCA RfP
4.2.10 | Service Charges |  | 
41 | Amendment of provision(s) relate to service charges as necessary | 14 | Engage with NEA during update of regulatory accounts, cost-of-service analysis, tariff application preparation
4.2.11 | Conducting Public Hearing |  | 
42 | Periodically hold public hearings to address public grievances in all provinces | 11 | Develop & implement public engagement & consultation policies & processes to ensure regular, transparent communication with power stakeholders & the public
BACK TO MAIN SLIDE