## Slide 1
Inception Meeting
Providing Consultancy and Program Management Services to Coal India Limited for Diversification and Value Addition
Coal India Limited
20 October 2020
Consulting

## Slide 2: Agenda for Discussion
Project Context
Project Plan & Timelines
Support needed from CIL
Team
Introduction
1.
2.
3.
4.

## Slide 3: Here with you today
Tushar Chakraborty
Project Leader
Associate Director,
Deloitte (India)
Over 14 years experience in the global mining & mineral industry.
He has also a First class mine manager’s certificate (Unrestricted/metalliferous) as certified by DGMS & RQP
Finance Lead
Sayantan Banerjee
Director,
Deloitte (India)
Over 21 years of experience in power sector consulting as well as coal power plant design/O&M
50+ engagements with governments, MFIs, thermal power gencos for Policy, B-plan, bid advisory, regulatory support
Arindam Guha
Deloitte Partner
Partner,
Deloitte (India)
Arindam is a partner with Deloitte with more than 22 years of experience
Arindam is also EXCO member and Government & Public sector lead for Deloitte
Specialist – Coal & Major mineral
More than 18 years of experience including 15 years’ experience in metals and mining sector
50+ engagements for governments, leading private sector and PSU companies. .
Rajib Maitra
Director,
Deloitte (India)
Specialist – Thermal Power
Anirban Bandyopadhyay
Project Manager
Manager,
Deloitte (India)
Over 12 years of experience including 6 years in coal power plant O&M and 6 years in power sector consulting covering conventional and RE generation
He is B.E. Power Engineering and MBA in Power Management
Project Associate - Technical
9+ years’ experience in exploration, resource planning, viability study for Coal, CBM, Iron Ore, Gold, etc. across India, Mozambique, Indonesia, PNG, Philippines, Nepal, Mauritania
He is M.Sc. In Applied Geology
Mainak Mukherjee
Senior Consultant,
Deloitte (India)

## Slide 4: Deloitte is world’s largest professional services firm, with rich experience of executing similar mandates in India
 | Strategy / market research / business plan | Due diligence/ feasibility studies | Regulatory support / Bid advisory | Strategic implementation
Coal / Major minerals / Metals |  |  |  | 
SCG/ C2C / CBM |  |  |  | 
Thermal power |  |  |  | 
Solar Energy |  |  |  | 
Mineral logistics |  |  |  | 
EBITDA Improvement / value addition |  |  |  | 
Representative clients & projects
REVENUE
US$47.6 Bn
RANKED #1 GLOBALLY IN CONSULTING1
SERVING BT 500 MINING AND METALS CLIENTS
9 of 13
MINING CENTERS OF EXCELLENCE
13
HEADCOUNT IN INDIA
50,000+
OFFICE ACROSS INDIA
14
PRESENCE IN COUNTRIES
150+
12019 ranking by Gartner based on Revenue and by IDC based on capability strategy
Notes: Credentialise Deloitte with saying more than 125+ similar engagements executed across ministries, PSE and Private clients

## Slide 5: Scope of work for the assignment
Diversification Areas
D1 - Surface coal gasification (SCG) based Coal-to-chemical Business
D2 - Utility-scale thermal power generation (Coal)
D3 - Solar power value chain (generation and backward integration)
D4 - Aluminium Smelting
D5 - Portfolio of non-fuel minerals through organic and inorganic growth
D6 - Coal Bed methane (CBM)
D7 - Mineral logistics
D8 - New Business Portfolio
Value Addition Initiatives
V1 - EBIDTA Improvement Initiatives (Quick Wins)
V2 - Shareholder value enhancement
V3 - Any set of activities / process (physical / financial), in any domain, that adds value to the Company based on emerging business environment / market dynamics
Module 1: Market research and Sectoral assessment
Module 2: Market entry strategy, Business modelling and Feasibility study
Module 3: Bid process management and selection of Project implementation agency for operationalising the qualified sector strategies.
Module 4: Program evaluation and Monitoring
Module 1: Identification of Value Addition Activity and Impact Assessment
Module 2: Framing of Implementation Plan
Module 3: Bid process management and selection of Project implementation agency for operationalising the qualified Value Addition Process / Activities.
Module 4: Program evaluation and Monitoring

## Slide 6: Overall Work Plan
 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Phase 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Module 1: Market Research and Sectoral Assessment For Activities D1, D2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
For Activities D3, D4 & V1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Module 2: Market Entry Strategy, Business Modelling and Feasibility Study For Activities D1, D2, D3, D4 & V1 (after CIL concurrence on Module 1 Final Report) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Phase 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Module 1: Market Research and Sectoral Assessment For Activities D5, D6, D7 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
For Activities D8, V2 & V3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Module 2: Market Entry Strategy, Business Modelling and Feasibility Study For Activities D5, D6, D7, D8, V2 & V3 (after CIL concurrence on Module 1 Final Report) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
In case CIL decides to proceed for Module 3 and 4 based on the outcomes of Module 1 and 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Module 3: Bid Process Management for selecting PIA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Module 4: Program Evaluation and Monitoring |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Months
Key Project modules
Kick-Off
Phase I closure
Phase II closure
Draft report
Selection of PIA
Module 3

## Slide 7
Key Activities and Outcome in the first 12 weeks
Areas
Activities
Outcome
  Team mobilization
  Interactions with stakeholders, surveys
  Data collection from CIL based on previous assignments
  Prioritise key diversification & value addition initiatives
  Initiatives prioritization
  Database for initiatives
  Framework for market research report
  Assessment of initiatives based on available information
  Study of trends for each initiatives including trade dynamics
  Technology and Regulatory trend analysis
  Market assessment and projections
  Market assessment report for prioritized initiatives
  Conduct opportunity diagnostic
  Identification and assessment of opportunities for quick win
  Assessment of opportunities for financial returns
  Preparatory activities (business case) for strategic options
  List of quick win initiatives
  Business case including potential EBITDA impact for such initiatives
Internal Assessment
External Assessment
Opportunities

## Slide 8
Team structure
Project Management and operating team
CIL management personnel
To be Defined
CIL
  Provide insight, coach and challenge project team on relevant matters and during workshop, critical interactions
  Visit based on prior approval of CIL management as per agreed rate
CIL professionals
  Representatives from CIL
  Provide inputs as well as coordinates leadership interactions as needed to understand constraints, capabilities & capacities
Coal Videsh 1
Coal Videsh 2
Technical
CMD office
Steering committee
Deloitte
CIL
To be Defined
CIL
CIL Project Manager
Specialists
Rajib Maitra
Coal & Major Mineral
Leadership Team
Tushar Chakraborty
Project Leader
Anirban Bandhopadhyay
Project Manager
Rakesh Surana
Engagement Partner & SME
Surbhi Patni
Project Associate - Finance
Mainak Mukherjee
Project Associate - Technical
Access to pool of consultants (need basis)
Shridhar Kamath
Partner & Specialist – EBITDA improvement
Sanjay Sah
Chemical
Sayantan Banerjee
Thermal Power
Peejush Naidu
Mineral Logistics
Amitabh Saha
Solar Energy

## Slide 9: Our governance structure
Type of review | Proposed date | Duration | Mode | Location | Agenda | CIL participants | DTTILLP Participants
Fortnightly status update meetings | Friday | 30 minutes | Physical | CIL HO, Kolkata | Discussion on progress Activities and deliverables during last two weeks Activities and deliverables planned for the coming week Key decisions / support required to manage progress as per targets | CIL SPOC from Coal Videsh team | Project Manager Associates (Technical & Finance)
Monthly update meetings | Friday | 1-2 Hours | Physical | CIL HO, Kolkata | Provide guidance and advise on the deliverables Provide feedback / decisions on the key observations Oversee the quality and progress of the engagement | Director(T) GM (CV) Other officials | Project Leader Project Manager Associates (Technical & Finance)
Steering Committee meetings | Once in 2 months | 1 hour | Physical/ Virtual | CIL HO, Kolkata | Escalate any critical issue / limitations observed during the course of assignment | CMD Directors CIL senior officials | Deloitte senior officials (need basis) Project Leader Project Manager

## Slide 10: Support needed from CIL
Infrastructure and Data Requirements
Working space for 4 - 5 team members along with locker
Telephone, internet (Wi-Fi) connectivity
Printer availability and connectivity
Projector availability
Sharing of relevant data requested as given in the Information Requirement List - reports, studies, organogram, plans, financials etc.
Communication/ Feedback Requirements
Identification of CIL single point of contact (SPOC) to facilitate necessary communication with other stakeholders.
Timely coordination of meetings with different CIL internal stakeholders as needed
Participation and feedback from senior CIL stakeholders in Steercom and Workshop meetings
Next steps
Completion of formalities related to Performance Bank Guarantee and Contract execution after requisite internal clearances
Mobilization of the site team members
Formal kick-off meeting after one week of mobilization

## Slide 11
Deloitte refers to one or more of Deloitte Touche Tohmatsu Limited, a UK private company limited by guarantee (“DTTL”), its network of member firms, and their related entities. DTTL and each of its member firms are legally separate and independent entities. DTTL (also referred to as “Deloitte Global”) does not provide services to clients. Please see www.deloitte.com/about for a more detailed description of DTTL and its member firms.
This material has been prepared by Deloitte Touche Tohmatsu India LLP (“DTTILLP”), a member of Deloitte Touche Tohmatsu Limited, on a specific request from you and contains proprietary and confidential information. This material may contain information sourced from publicly available information or other third party sources. DTTILLP does not independently verify any such sources and is not responsible for any loss whatsoever caused due to reliance placed on information sourced from such sources. The information contained in this material is intended solely for you. Any disclosure, copying or further distribution of this material or its contents is strictly prohibited.
Nothing in this material creates any contractual relationship between DTTILLP and you. Any mutually binding legal obligations or rights may only be created between you and DTTILLP upon execution of a legally binding contract. By using this material and any information contained in it, the user accepts this entire notice and terms of use.
©2020 Deloitte Touche Tohmatsu India LLP. Member of Deloitte Touche Tohmatsu Limited
Deloitte Touche Tohmatsu India Private Limited (U74140MH199 5PTC093339), a private company limited by shares, was converted into Deloitte Touche Tohmatsu India LLP, a limited liability partnership (LLP Identification No. AAE-8458),with effect from October 1, 2015.
End of Presentation.

## Slide 12: ANNEXURES

## Slide 13: Our proposed team to execute this assignment
Chart: 
| 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr
Sales | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632
Chart: 
| 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr
Sales | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632
Chart: 
| 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr
Sales | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632
Chart: 
Chart: 
| 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr
Sales | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632 | 5.2632
Bringing together the best of Deloitte Leadership and Teams
DEBASISH MISHRA
PARTNER,
ENERGY & RESOURCES LEADER
ARINDAM GUHA
PARTNER, GOVERNMENT & PUBLIC SECTOR LEAD
EXCO member
PEEYUSH NAIDU
PARTNER
Specialist- logistics
SHRIDHAR KAMATH
PARTNER
Specialist- EBITDA improvement
RAKESH SURANA
PARTNER,
MINING & METALS LEADER
TOM ALDRED
PARTNER
Global SME - Chemical/ Process Industry
SAYANTAN BANERJEE
DIRECTOR
Specialist- Thermal Power
SURBHI PATNI
SENIOR CONSULTANT
Project Associate- Finance
TUSHAR CHAKRABORTY
ASSOCIATE DIRECTOR
Project Leader
ANIRBAN BANDYOPADHYAY
MANAGER
Project Manager
MAINAK MUKHERJEE
SENIOR CONSULTANT
Project Associate-Technical
RAJIB MAITRA
DIRECTOR
Specialist-Coal & Major Mineral
24+
22+
23+
25+
27+
22+
22+
18+
20+
22+
17+
14+
12+
6+
9+
GLOBAL EXPERTS
PROGRAM LEADERSHIP
SPECIALISTS
SITE TEAM
Available today
ANDREW SWART
PARTNER,
METALS & MINING SME-GLOBAL
Global Mining SME
EXPERIENCE
SANJAY SAH
PARTNER
Specialist- Chemical
AMITABH SAHA
DIRECTOR
Specialist- Solar Energy

## Slide 14: Overall approach covering diversification and value addition initiatives
Draft preliminary hypotheses on the shortlisted diversification areas
Conduct deep industry analysis to prioritize areas and articulate areas of play, how to play and strategic relevance
Prioritization based on CIL’s competencies and organizational gaps, mission and vision
2
Hypotheses building and mapping them to suitable action items
3
4
1
Identification of the Sectoral Scenarios of Major Diversification Areas
Derive the Strategy to Penetrate
Onboarding of Project Implementation Agencies (PIA)
Program Monitoring and Evaluation
Identify plausible interventions and support required in policy level, organization level and stakeholder level
Analyze interventions to policies, manpower in-force and list considerations for framing implementation strategy
Risk Assessment and Mitigation Plan
Build target operating model and operationalization plan for PIA;s for implementing strategic goals
Map them to bidding documents
Bid process management support for onboarding the PIAs
Develop action plan for PIAs
Mapping of a Project Management Framework with teaming and reporting structure
Develop PEMO tool
Issue Management and Mitigation Support
Project timeline and cost evaluation and monitoring
Implication led research on underlying issues and interventions
Identification of the market scenario, Opportunity and Challenges
Design components of project management and PMO support
EBIDTA Improvement
Shareholder Value Enhancement
Process Intervention assessment for emerging markets
Value Addition Initiatives

## Slide 15: Module 1: Market Research and Sectoral Assessment
Market Scenario
Risk
Competition
Projections and Outlook
Key Focus areas of the target Areas and Markets
Opportunities and Challenges
Developing the Action Items
Identification of Potential areas of play
Assessment of As-Is Scenario for competency
Identification of Key Areas for Developing Strategy
Aligned with CIL’s mission and vision?
Meeting Diversification goals?
Positional advantages?
Matching Core competency?
Skill-benchmarking Requirement
Structural interventions required?
Process Changes?
Gaps in the process
Strategic interventions required
Prioritize the areas of play
Market Assessment Check-List
Demand Supply scenario
PRESTL Analysis
Value Chain Assessment
Key Players and Competition
Overall contribution in economy
Financial condition
Raw Material and Value Chain analysis
Key Risks
Macro Scenario
Existing business model
Advantages and disadvantages of current models
Innovative models
Case studies and learnings
Market Strategies
Margin assessment
Assessment of the financials of the key players
Profitability assessment
Cost of raw material
Cost optimization initiatives
Investment flows in the market
Financial
Land Availability
R&R requirement
Connectivity
Basic Infrastructure availability
Location and High-Level feasibility
Projected growth
Planned capacity addition
Plan to mitigate demand-supply gap
Government policy trajectory for the sector
Shareholders sentiment towards the sector
Outlook
Digital penetration Level
IT & Digital
EHS related concerns
Environment, Health & Safety
Key Principles for Areas of Play
Illustrative Market Assessment
Illustrative
Organizational Competency
Strategic Relevance Assessment

## Slide 16: Module 2: Developing Strategies
Chosen
strategy
Financial position
Strategic position
Capital market
Economic profitability
Growth
Commercial market
Market attractiveness
Competitive position
Insight
Organizational Transformation
Implementation Plan
Infrastructure Requirement Analysis
Strategic
issues
Organizational Competency
Develop Business Models
Scenarios and options
Module 2: Developing the strategies for market penetration of the shortlisted models

## Slide 17: Module 3: Preparation of RFP for Selection of PIA
Once CIL Management decides to go ahead with the diversification plan, Deloitte will assist CIL in drafting the RFP for selection of PIA
Deliverable
Illustrative areas to be covered in the RFP for PIA Selection
Staged delivery schedule
Mode of bidding (limited/open).
Procurement methods (Quality cost basis, Lowest bid, highest technical, etc.)
Evaluation Criteria
Definition of Performance Parameters and Performance Levels to be met by the PIA
Definition of Scope of Work and Deliverables with High Level Project Plan
Process Description and Functional Requirement Specifications categorized as Critical, Essential, Desirable
Capacity Development Plan
Post implementation support requirements at locations with service level specifications
Performance Guarantee, Warranty requirements (as needed)
Nature of system documentation required (operational, system and user level)
General and Special terms and conditions governing the RFP
The first step in the ERP Implementation is the preparation of an RFP for selection of ERP package and Implementation partner
Sample Bidding Documents

## Slide 18: Module 3: Preparation of RFP for Selection of PIA
Based on developed draft biddable RFP, Deloitte will assist CIL in selection of Project Implementation Agency (ies) (PIA) based on a defined process.
Evaluation criteria in RFP
Review the RFPs, working towards a scoring consensus between evaluators
Complete relevant sections of the scoring matrix
Formulate questions during review
Consolidate questions and submit to vendors
Vendor Demos
Vendors present their solution using the demo scripts
Vendors respond to the additional RFP questions
Review demos & ranking
Review vendor demos and achieve scoring consensus
Complete evaluation matrix
Review preliminary ranking calculated by scoring matrix
Consider composite solutions
Prepare shortlist and request site visits
Final evaluation of solutions
Finalise PIA evaluation
Prepare Business Case for the vendor selection and present the same to the management
The second step in the ERP Implementation is the evaluation of the bids received from Project Implementation agencies
EVALUATION SCORE MATRIX
Illustrative

## Slide 19: Module 4: Four pronged approach to drive program execution and ensure timely implementation
Policy change log management
  Centralized change log tracker :Logs to capture changes suggested by stakeholders in various meetings
  Prioritization criteria: Criteria to prioritize the various inputs for action to facilitate the agreement
  Version Control: Version control of policy to facilitate the work allocation and consolidation
Governance, Monitoring & Tracking mechanism
  Governance structure: Set up the Program hierarchy & decision making
  Key Risks : Critical risks are highlighted to leadership to gain alignment on mitigation measures
  Critical Milestones: Document all critical milestones indicate progress towards each
  Communication & feedback Management
  Policy Communication Plan : High level plan to communicate the changes and progress of changes to internal and external stakeholders
  Communication Content Approval Process : Structured process which will enable the communication content for communication of information
1
2
3
Overall Program Management
3
Governance, risk & milestone tracking
Policy change log management
Dashboard to monitor KPI’s & plan Corrective actions
Communication & feedback management
1
2
3
4
  Dashboard to monitor KPI’s & plan Corrective actions
  Program KPIs : Setup measures of success and dashboard view of project status
  Roll-up Summary Dashboards : Provides summary view of all KPIs, activities, work-stream status, interactions planned versus actual for each work-stream.
4

## Slide 20: Module 4: Setting up of the PMO & Implementation Monitoring Framework
The scope is defined, realistic and actively monitored
Deliverables and approval process are defined and clear
Quality standards are defined and monitored
Work is planned and tracked, and critical path is monitored
Team is competent, motivated and exemplary
All stakeholders are involved
Costs are monitored and expected gains have been measured
Risks are anticipated and mitigation actions are triggered on time
1
2
3
4
5
6
7
8
Consistency and Delivery Excellence
Risk Management
Scope Management
8
7
6
5
4
3
2
1
Deliverables Management
Cost Management
Communication Management
Quality Management
Human Resource Management
Time Management
Documentation during program management
Detailed list of activities to be actioned (current week and next week) with completion dates and responsibility owners to be published every week before Friday EOD
Action Log
Review of the project in presence of key stake holders – CIL Management, and project management team and send monthly review report
Monthly review
Identify the risk items which have the potential to hamper the project outcomes with action plan to mitigate the same – to be highlighted to CIL project team and respective Vendor
Risk Log
Prepare the outcome analysis report consisting of the detailed assessment of the tangible and intangible benefits achieved by CIL from each diversification initiative
Outcome analysis reports
Monitor timely implementation and prepare implementation status report
Assessment of project finance, costing and financial status
Timeline and Financial Log
Illustrative Approach

## Slide 21: Module 4: Approach for Risk Management
Risk Assessment Score - After assessing the probability and impact, Risk score is determined by multiplying the probability rating by impact rating. This gives a score based on which these are Priority-categorized and put on a matrix and the ones with highest priority are taken care of first
3. Risk Matrix and Issue Prioritization
1. Issue Identification
2. Issue Evaluation and Scoring
Occurrence
An assessment on the probability of an event / risk occurring. A rating of defined scores across categories shall be used:-
Level | Description
1 | Almost Certain
0.8 | Likely
0.6 | Possible
0.4 | Unlikely
0.2 | Rare
Criticality
The impact or consequences on the ERP implementation project if the event was to occur. Assuming the risk has materialized, assessment of impact in terms of: Cost, delays, security of data, and reputation and is rated with designated weighted scoring
Illustrative
Level | Description
5 | Critical
4 | High
3 | Medium
2 | Moderate
1 | Low
Illustrative
Project Boundary
Project Finance
Business/ Organization
Project Timelines/ Delivery
Un-optimized resource Planning
Reporting Issues
Payroll processing
Cost Overrun
Low rate of return
Higher borrowing rate
Un-optimized spending
Inappropriate contract terms
Non-binding contract
Lack of contract monitoring
Supply Issues
Inventory lags
Vendor Management Issues
Resource
Constraints
Project and O&M Issues
Financial Issues
Contractual Issues
Contract/ Commitment
Impacting Issues
There are a number of issues that have a manifold impact over the organization and business
Issues Listing
We will critically assess and list the issues that creates an impact in CIL’s business and organization