## Slide 1
Selection of Transaction Advisor for Assessment of Institutional Development and Human Resource Management of The Durgapur Projects Limited (DPL)
RFQ NO: WBDPL/PUR/CORP/RFQ/110/2021-2022
The Durgapur Projects Limited
Contractual Deliverables –
Final Report
To – be and Recommendations
  (Manpower Planning, Organization Structure, Performance Management System (PMS), KPIs, and Outsourcing Models)
Redesigned Training Policy & Plan.
Capacity Building Plan including revised KPIs & MIS
31st March 2023
© Deloitte Touche Tohmatsu India LLP

## Slide 2
CONTENT
 | Project Context Our understanding of the project
 | Progress So Far Summary of key deliverables submitted so far
 | Project Timelines Current status of project timelines and alignment with work plan
 | Benchmarking Study Key Insights from benchmarking with other utilities
 | Focus Areas wise To-Be Reports Key Insights and recommendations for each focus area
 | Annexures
1
2
3
4
5
6

## Slide 3: Project Deliverables Timelines as per RFP - Phase 1 Work Plan (Week 01 – Week 24)
A structured approach to engaging key stakeholders across the organization to achieve desired results
Deliverable | Timeline from Start of Assignment
Submission of Inception Report | 03 Weeks
Report & presentation on the As – Is structure, manpower, etc. | 10 Weeks
Report & presentation on To – Be and recommendations | 16 Weeks
Report & presentation on the As – Is Training Policy & Plan. | 16 Weeks
Report & presentation on the Redesigned Training Policy & Plan. | 20 Weeks
Report & Presentation on Capacity Building Plan including revised KPIs & MIS | 22 Weeks
Updated manuals and Final Report submission | 24 Weeks

## Slide 4: Key Deliverables Timelines
Details on submission of key deliverables
Key Deliverables as per RFP | Key Deliverables as per RFP
 | Inception Report
 | As-Is Assessment on structure, manpower etc.
 | As-Is Training Policy and Plan
 | Report & presentation on To – be and recommendations
 | Report & presentation on the Redesigned Training Policy & Plan
 | Report & Presentation on Capacity Building Plan including revised KPIs & MIS
 | Updated manuals and Final Report submission
A
B
C
D
E
Deloitte’s Deliverable Submission Approach | Deloitte’s Deliverable Submission Approach | Submission Date/Timelines
 | Inception Report | September 08, 2022
 | As-Is Assessment, As-Is Training Policy & Plan | Draft Version - Oct 14, 2022 Revised Version - Nov 03, 2022 Final version – Dec 12, 2022
 | Human Resource and Organization To-Be Report & Redesigned Training Policy and Plan | Working Papers for the various deliverables were submitted earlier. Final Report submitted on March 31, 2023
 | Report on Capacity Building Plan including revised KPIs & MIS | Ongoing (Focus Area wise to-Be reports to be submitted for review)
 | Updated manuals and Final Report submission | Ongoing
A
B
C
D
F
G
E
Completed

## Slide 5: Timeline for Key Discussions, Submissions & Presentations (1/4)
List of key timelines with regards to benchmarking study with other utilities and discussions on finalization of To-Be reports
Sl. No | Date | Key Event
1 | October 14, 2022 | Draft version of As-Is Report, Questionnaire and Letter to connect with other utilities submitted
2 | October 18, 2022 | Discussion on draft As-Is report and resharing of Questionnaire and Letters to connect with other utilities for benchmarking.
3 | November 03-04, 2022 | Discussion with MD and Project Nodal team on final As-Is Report and way forward to To-Be. Respective report was shared on Nov 03, 2022.
4 | November 9, 2022 | Letters received from DPL for benchmarking studies with WBSETCL,WBPDCL,DVC and WBSEDCL.
 |  | DPL Project Nodal/Advisory Team to provide additional areas/changes to be covered in As-Is Report.
5 | November 9, 2022 | Deloitte coordinated with designated utilities’ POCs for discussion on benchmarking study, accordingly meetings were setup with DVC and WBSETCL on Nov 17 and 22, respectively. However, meetings couldn’t be setup with WBSEDCL and WBPDCL. Deloitte team called WBSEDCL twice (Nov 9 and 11) but POC unavailable
6 | November 16, 2022 | Deloitte team met Director HR (WBPDCL). Director HR (WBPDCL) nominated GM HR for conducting the interviews
7 | November 17, 2022 | First round of discussion with Mr. N.V Ramana, Chief Engineer (HR)-DVC as part of benchmarking study. He provided high-level verbal inputs on benchmarking areas.
8 | November 19, 2022 | Tried reaching out Mr. N.V Ramana, Chief Engineer (HR)-DVC for second round of discussion but meeting could not be fixed due to his prior appointments
9 | November 22, 2022 | Discussion carried out with Executive Director (HR)-WBSETCL as part of benchmarking study. A few documents were shared by WBSETCL and remaining were proposed to be shared in second round of discussion. WBSETCL Officials Met - Mr. Shamya Roy Choudhury, Director (HR&A), Mr. Sujoy Goswami, AGM (HR&A)
10 | November 22, 2022 | Tried reaching out Mr. N.V Ramana, Chief Engineer (HR)-DVC for second round of discussion but meeting could not be fixed due to his prior appointments

## Slide 6: Timeline for Key Discussions, Submissions & Presentations (2/4)
List of key timelines with regards to benchmarking study with other utilities and discussions on finalization of To-Be reports
Sl. No | Date | Key Event
11 | November 23, 2022 | Deloitte was asked to visit DVC office for second round of discussion. Deloitte visited DVC office for meeting, but discussion could not be held due to unavailability of CE-(HR), DVC
12 | November 25, 2022 | Second round of discussion with Mr. Sujoy Goswami, AGM (HR&A), WBSETCL. Relevant data for key benchmarking focus areas collected.
13 | November 26, 2022 | Second round of discussion with CE (HR)- DVC was held , few documents were shared by DVC on key focus benchmarking areas and other documents yet to be received.
14 | December 2, 2022 | Discussion with Mr. Saurav Bhattacharjee, Manager (HR&A) - WBPDCL for data collection on key focus benchmarking areas. Verbal inputs at a high level were received.
15 | December 6, 2022 | Received data pertaining to WBSEDCL from DPL on the key focus areas for benchmarking.
16 | December 12, 2022 | Followed-Up with Mr. Saurav Bhattacharjee, Manager (HR&A) - WBPDCL for data collection on key focus benchmarking areas. No documents received yet
17 | December 12, 2022 | Deloitte submitted the revised final version of As Is report incorporating comments received during discussions on Nov 04, 2022, with MD and Senior DPL Management and Dec 06, 2022, with Project Nodal Team.
18 | December 13, 2022 | Visited WBSEDCL office for pending data points for Benchmarking. Provided the Scanned copy of DPL letter and Key focus areas for benchmarking to WBSEDCL.

## Slide 7: Timeline for Key Discussions, Submissions & Presentations (3/4)
List of key timelines with regards to benchmarking study with other utilities and discussions on finalization of To-Be reports
Sl. No | Date | Key Event
19 | December 16, 2022 | High level data pertaining to Manpower Planning, PMS, KPI’s focus areas were received from Mr. Saurav (WBPDCL). Deloitte requested to provide pending data points on organization structure, training plan/policy and outsourcing activities/policy. A meeting with Training section has been requested.
20 | December 16, 2022 | A telephonic conversation with Mr. Sabyasachi De (GM, HR&D - WBSEDCL) for data collection and discussion on benchmarking study. He agreed for a discussion on December 20, 2022.
21 | December 19, 2022 | Tried reaching out Mr. Saurav, WBPDCL for setting up meeting with training section of WBPDCL. No response received.
22 | December 19, 2022 | Deloitte team requested Mr. S Mukherjee, SM, DPL for guidance and coordinating with WBPDCL for data collection in benchmarking study.
23 | December 19, 2022 | A telephonic Meeting finalized with Mr. NV Ramana, Chief Engineer (HR) - DVC for data collection
24 | December 19, 2022 | Meeting finalized on December 20, 2022, with Mr. Sabyasachi De (GM, HR&D - WBSEDCL) for data collection and discussion on benchmarking study
25 | December 20, 2022 | Meeting held with GM (HR&A) Mr. Sabyasachi (WBSEDCL), Received Training Calendar/Plan and other data pertaining to training and development. Data regarding to Manpower details of regular as well as Outsourced agency to be provided by Contract Labour Management (CLM) Cell. Discussions with other stakeholders were scheduled for December 21, 2022
26 | December 20, 2022 | Telephonic Meeting could not be held with Mr. NV Ramana, Chief Engineer (HR)-DVC , due to his unavailability.
27 | December 21, 2022 | Meeting held with AGM (HR&A) Mr. Siladitya Sengupta (WBSEDCL). Received Outsourcing employee data, PAF (Class I,II and III), Manpower Strength Department Wise. For detailed manpower details, Deloitte team met Mr. Podder who agreed to share the relevant data soon.
28 | December 22, 2022 | Detailed breakup of manpower strength received from R&MP Cell, WBSEDCL

## Slide 8: Timeline for Key Discussions, Submissions & Presentations (4/4)
List of key timelines with regards to benchmarking study with other utilities and discussions on finalization of To-Be reports
Sl. No | Date | Key Event
29 | January 03, 2023 | Discussion with Mr. N.V. Ramana (CE – DVC, HR&A) on collection of data for respective focus areas. In the discussion, Mr. Ramana agreed to share the necessary data with DPL over email.
30 | January 03-06, 2023 | Deloitte team coordinated with DPL for collection of data received from DVC stakeholders.
31 | January 07, 2023 | Deloitte team collected data from Mr. N.V. Ramana (CE – DVC, HR&A).
32 | January 13, 2023 | Deloitte team collected high level verbal inputs from Mr. P.S. Chatterjee (GM – WBPDCL, HR&A).
33 | January 17, 2023 | Deloitte presented To-Be reports on PMS, Training & Outsourcing models focus areas to HR project nodal team led by GM HR&A, DPL. The received inputs/feedbacks to be incorporated in revised version.
34 | January 18, 2023 | Deloitte presented To-Be reports on PMS, Training & Outsourcing models focus areas to MD and Director Finance, DPL and discussed way forward.
35 | February 01, 2023 | Deloitte team presented To-Be working papers to MD and Director Finance, DPL and took guidance for way forward.
36 | February 02, 2023 | Deloitte presented To-Be reports on PMS, Training & Outsourcing models focus areas to MD and Director Finance and DPL HR Core team.
37 | February 07, 2023 | Deloitte presented To-Be reports on Key Performance Indicators (KPI’s) and Manpower Planning focus areas to MD and Director Finance.
38 | March 14, 2023 | Deloitte presented To-Be report on Organization Structure to MD and Director Finance at DPL Office, Kolkata.
39 | March 31, 2023 | Deloitte presented the Final To-Be report on Organization Structure to MD and Director Finance at DPL Office, Kolkata.