## Slide 1: Headline Verdana Bold
Deloitte Touche Tohmatsu India LLP, November 2021
Strategic planning and transformation of the West Bengal Power Sector
Project Inception
Department of Power, Government of West Bengal
Notes: To be picked from https://consulting.deloitteresources.com/brand/Pages/Imagery.aspx
https://brandspace.deloitte.com/content/index/guid/image_library?search_term=&list_size=25&assettag%5B16%5D%5B%5D=43&assettag%5B19%5D%5B%5D=50

## Slide 2: Agenda for the Day
Engagement Phasing
1.
Project Deliverables
2.
About Inception Report
3.

## Slide 3: Engagement Phasing
Phase-1
Phase-2
Module-1: Comprehensive diagnostic review and causal analysis (details)
Module-2: Development of strategic vision 2030 and priorities (details)
Implementation Support (details)
24 weeks (6 months)
72 weeks (18 months)

## Slide 4: Our Understanding of Project Objective and Statement of Work
Deliverables
Deliverable | Timeline from start of assignment
PHASE-1: | 
Inception report | 2 weeks
Module-1 Subcomponent-1: Assessment of West Bengal Power Sector: | 8 weeks
Report and Presentation on Operational and Financial performance(As-Is) | 
Report and Presentation on Regulatory performance(As-Is) | 
Report and Presentation on ongoing projects and proposed projects(As-Is) | 
Module-1 Subcomponent-2: Assessment of external factors on West Bengal Power Sector: | 12 weeks
Report and Presentation & financial model on Power demand and supply trends – future outlook & Key Growth drivers for the state’s power sector and their Sustenance | 
Report and Presentation on Emerging sector trends and their influence/implications on power Sector | 
Module-1 Subcomponent-3: Report & presentation on interactions with Stakeholders | 16 weeks
Module-1 Subcomponent-4: Report and Presentation on SWOT analysis | 
Module-2 Subcomponent-1: Report and Presentation on Power sector vision development for 2030 | 24 weeks
Module-2 Subcomponent-2: Report and Presentation on key strategic priorities and actions | 
Module-2 Subcomponent-3: Report and Presentation on detailed action plan | 
PHASE-2: | 
Quarterly reports on the progress and deliverables on Implementation and Monitoring support of Vision, Roadmap and the turnaround plan | Quarterly over 18 months’ period

## Slide 5: Our Understanding of Project Objective and Statement of Work
About the Inception Report
Purpose of the report
To introduce the project and explain the project objectives and work plan
To summarize the work done during the preliminary / kick-off phase
What the report covers
Project objectives and work plan
Activities performed during kick-off phase and Preliminary insights derived from kick-off discussions
Preliminary information requirement list
What the report is not intended to cover
As-is analysis of the utilities
Any recommendation on way forward / action plan
Way forward – Immediate next step
Analysis of historical operational and financial performances of utilities
Understanding the key challenges (along with underlying drivers) and priority areas upon consultation with utilities
Identification of areas of further improvements and Submission of as-is reports

## Slide 6: Thank You

## Slide 7: Annexure – Scope of Work

## Slide 8: Scope of Work Phase-1: Module-1
Module-1 (Comprehensive diagnostic review and causal analysis)
Task 1: Assessment of Financial and Operational Performance of state utilities
Task 2: Assessment of Regulatory Performance
Task 3: Review of impact of past, on-going & proposed State / Central Schemes in WB
Sub-component 1: Assessment of West Bengal Power Sector
Sub-component 2: Assessment of external factors on WB Power Sector
Task 1: Power demand and supply trends, future outlook and key growth drivers for the state’s power sector and their sustenance
Task 2: Emerging sector trends and their influence/implications on power sector
Sub-component 3: Interactions with stakeholders
Sub-component 4: Comprehensive SWOT analysis of the sector
Interact with internal stakeholders like Sr. Mgmt. of Utilities, Heads of corporate functions, and Business Unit Heads
Holding consultations with the staff of the power department/utilities and external stakeholders like the state government, regulator and principal consumers etc
Carry out a SWOT analysis of the sector based on the above analysis & feedback from internal/external stakeholders
Week 0
Week 16
BACK

## Slide 9: Scope of Work Phase-1: Module-2
Prepare a roadmap for implementation of each initiative that would result in financial and operational improvement with definite timelines and responsibilities.
Identification of activities with measurable and target oriented Key Performance
Indicators (KPI) to demonstrate the effectiveness of the action plan
Development of business case and implementation roadmap for each initiative
Development of effective monitoring and evaluation framework with adequate governance mechanism.
Sub-component 3: Development of detailed action plan identifying roles and responsibilities of key stakeholders
Week 24
…Continued from Previous Slide
Module-2 (Development of strategic vision 2030 and priorities)
Formulation of vision statement for West Bengal State Power Sector
Identification of goals specific to the State necessary to fulfill the vision
Sub-component 1: Power sector vision development for 2030
Develop strategic initiatives under each goal to help achieve the overall vision and identify critical enablers including policy reforms for achieving goals set by the State
Facilitate overall coordination with Utilities and assist in stakeholder interaction for development of Resources vision
Sub-component 2: Detailing of the vision into the key strategic priorities and actions
BACK

## Slide 10: Scope of Work Phase-2
Implementation Support
Post finalization of Vision, roadmap and turnaround strategy, support to Department of Power, Government of West Bengal in implementation of the approved turnaround strategy and in monitoring the KPIs and timelines.
The scope includes the following:
i. Support in implementation of the respective goals, specific initiatives and turnaround plans
ii. Development of project management dashboards for project level monitoring
iii. Providing periodic status and update to Department of Power
Implementation and Monitoring support of Vision, Roadmap and the turnaround plan
Implementation support by coordinating with other Utilities
Week 96
…Continued from Previous Slide
BACK

## Slide 11: Our Understanding of Project Objective and Statement of Work
To assess the key cost-drivers and factors influencing the financial, operational and regulatory performances of West Bengal power utilities
To evaluate potential impact of emerging sector trends and Govt. programs / schemes on performance of the state power utilities
To create a state sector vision, identify action items and formulate actionable roadmap for achieving financial sustainability of the utilities and seamless transitioning with the emerging sector trends
Objectives
External environment
How will the power demand-supply scenario of West Bengal change in the medium and long term?
How are the state power utilities placed in embracing the emerging sector trends?
What will be the potential impacts of various Govt. schemes on utility performances?
What are the key drivers behind the current financial, operational and regulatory performance of state power utilities?
What are the current performance challenges and potential measures to overcome those?
Internal challenges
Key questions
What will be the strategic priorities to ensure financial sustainability of state utilities ?
Roadmap
Project Objectives and Key Questions to be Answered
BACK

## Slide 12: Annexure – Work Plan

## Slide 13: Our Integrated Work Plan for the Project
W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24
Phase-1
Phase-2
72 Weeks
Time line
Legend:
Deliverables
Submission of Inception report
Report & Presentation on Operational & Financial performance (As-Is)
Report & Presentation on Regulatory Performance (As-Is)
Report & Presentation on ongoing projects & Proposed projects (As-Is)
Report & Presentation & financial model on Power demand & supply trends
Report & Presentation on Emerging sector trends & their impact on power sector
Report & presentation on interactions with stakeholders
Report & Presentation on SWOT analysis
Quarterly report over 18 month’s Period
Deliverables
Report & Presentation on Power sector vision development for 2030
Report & Presentation on key strategic priorities and actions
Report & Presentation on detailed action plan
Key Activities / Milestones
MODULE-1: Diagnostic Review & Causal Analysis
MODULE-2: strategic vision development
Assessment of Financial and Operational Performance
Inception Report
Assessment of Regulatory Performance
On-going & Proposed Project Review
Power demand and supply trends–future outlook and key growth drivers for the state’s power sector and their sustenance
Emerging sector trends and their influence/implications on power sector
Continuous Stakeholder Interaction
Comprehensive SWOT analysis of the sector
Power sector vision development for 2030
Detailing of the vision into the key strategic priorities and actions
Development of detailed action plan identifying roles and responsibilities of key stakeholders
Implementation and Monitoring support
of Vision, Roadmap and the turnaround plan
Develop Monitoring framework
Implementation and monitoring support
Stakeholder interaction

## Slide 14
Deloitte refers to one or more of Deloitte Touche Tohmatsu Limited, a UK private company limited by guarantee (“DTTL”), its network of member firms, and their related entities. DTTL and each of its member firms are legally separate and independent entities. DTTL (also referred to as “Deloitte Global”) does not provide services to clients. Please see www.deloitte.com/about for a more detailed description of DTTL and its member firms.
This material has been prepared by Deloitte Touche Tohmatsu India LLP (“DTTILLP”), a member of Deloitte Touche Tohmatsu Limited, on a specific request from you and contains proprietary and confidential information. This material may contain information sourced from publicly available information or other third party sources. DTTILLP does not independently verify any such sources and is not responsible for any loss whatsoever caused due to reliance placed on information sourced from such sources. The information contained in this material is intended solely for you. Any disclosure, copying or further distribution of this material or its contents is strictly prohibited.
Nothing in this material creates any contractual relationship between DTTILLP and you. Any mutually binding legal obligationsorrights may only be created between you and DTTILLP upon execution of a legally binding contract. By using this material and any information contained in it, the user accepts this entire notice and terms of use.
©2021 Deloitte Touche Tohmatsu India LLP. Member of Deloitte Touche Tohmatsu Limited
Deloitte Touche Tohmatsu India Private Limited (U74140MH199 5PTC093339), a private company limited by shares, was converted into Deloitte Touche Tohmatsu India LLP, a limited liability partnership (LLP Identification No. AAE-8458),with effect from October 1, 2015.