## Slide 1
Deloitte Touche Tohmatsu India LLP
WBDPL/NITE/GM(T)/ITC/166/3-Engagement of an ERP Roadmap Consultant
The Durgapur Projects Limited
Kick-Off Presentation
April 2022

## Slide 2
COVERAGE
 | Project Context Our understanding of the project
 | Scope of Work Summary of the scope and key deliverables
 | Our Approach and Methodology Key considerations for our approach and methodology
 | Work Plan Summarized activities and delivery timelines
 | Next Steps Way Forward
1
2
3
4
5

## Slide 3: Project Context
With technological advancements and ever-growing business demands, the business opportunities and efficiency for DPL lies in integration of its business processes through ERP
Initial discussions with DPL
Several aspects would need to be studied such as
(i) Identification of improvement opportunities for existing business processes and IT Infrastructure (ii) Cost assessment of ERP implementation (iii) identifying Implementation challenges and addressing them upfront.
Existing IT systems not catering to key business functionality and business requirements
Difficulty in integration of existing IT systems from diversified software components
As per Microsoft, FoxPro software has reached end of life and future support will be limited
No automated system for generating MIS. Reliance on manual data collection and reporting for MIS
Requirement of systems for Human Resource Management, Material Management , Finance, Plant O&M
Challenges
Existing System
It is in this context that DPL looks forward to evaluating a comprehensive ERP package
FoxPro Software
Stores Accounting
Final Accounts
License fee & Water bill generation
Java/Oracle Software
Payroll Mgt
PPF, Wages, Treasury and Cash.
Fly Ash and Pond Ash. Plant MIS portal
File tracking system and Website DPL
GST Return software and E-invoicing
Accounts payable and Enquiry portal.
Support management software and GST Return Software.
Java/SQL Software
Tariff and tender portal
Environmental data portal
ALCD portal and inside plant billing
Need to finalize the future application roadmap at the earliest

## Slide 4: Summary of Scope of Work (1/2)
We understand that the objective of this assignment is to assist DPL in identifying business requirements, assessing feasibility of ERP implementation with a roadmap
Proposed Scope of Work
Functional Requirement Specifications
Feasibility Study
  Results
  As-Is Study/Assessment (Business Process & Existing IT Infrastructure)
  Discussion with DPL Departments to understand requirements and current challenges
  Identify and detail ERP requirements for identified functions
  Prepare draft Functional Requirement Specifications (FRS)
  Discussion and feedback from DPL to finalize Functional Requirement Specifications (FRS) for ERP implementation
  Preparation of Road Map Blueprint for ERP Implementation
  Conduct feasibility study for ERP implementation at DPL’s
  Assess challenges in ERP Implementation and identify issues, risks, and their mitigation steps
  Prepare cost assessment for ERP implementation at DPL
  Feedback from DPL to finalize To-Be design’s FRS for ERP implementation
  Selection of ERP Implementation Agency (IA) & Program Management
  Preparation of bid documents for ERP solution & Implementation Agency
  Advise DPL on evaluation and selection of bidders
  Coordination between DPL and the Implementation Agency staff
  Monitor, supervise and guide the implementation process
  Post implementation review
  Note - Detailed Scope of Work to be followed as per the tender document throughout the course of assignment

## Slide 5: Summary of Scope of Work (2/2)
Conduct As-Is assessment and design to-be processes for each functional area for inclusion in requirements
Human Resource Management – Master Data Preparation
Material Management
Sales & Distribution Management
Financial Accounting and Management
Plant Operation & Maintenance Management including permit to work module
Key aspects to be covered for Functional Study
  Note - Detailed Scope of Work to be followed as per the tender document throughout the course of assignment
Functional Areas under the proposed ERP system and Key Considerations
As-is assessment of the existing business processes vis-a-vis. best in class practices
Assess ways of integrating existing processes, systems with proposed ERP system
Listing changes in business processes required and effort in affecting those changes before implementing ERP
Design of to-be business processes required for affecting changes
Assess need for Customization vis-a-vis ERP products available in market
Develop functional requirements specifications which are critical for development of RFP

## Slide 6: Our Approach and Methodology (1/2)
Functional Requirement Specifications (FRS) – Regular discussions would be held with different DPL departments. Removing process inefficiencies and brining process improvements will be the key priorities
Integrated
Operate across the entire value chain.
Operations include exploration, production, transportation, refining/ processing and marketing of oil, natural gas, and petroleum products.
Many include petrochemicals.
Upstream (Exploration & Production)
Acquisition, exploration, and development of properties for production of crude oil and natural gas from underground reservoirs
Oilfield Services
Supplying manufactured equipment, technology and services related to evaluation of hydrocarbon formations, drilling and completion, production, transportation of oil and natural gas.
Offshore installations, marine oil and gas carriers
Midstream (Transportation & Storage)
Gathering, processing, storage, and transmission of natural gas and crude oil
Transportation, fractionation and storage of petroleum products and natural gas liquids (NGLs); Liquefied Natural Gas (LNG) and Liquefied Petroleum Gas (LPG) carriers
Downstream (Refining, Trading & Marketing)
Refining crude oil into various hydrocarbon products including gasoline, jet fuel, fuel oils, and diesel
petrochemicals production by integrated oil companies.
Marketing and trading products through wholesale and retail channels

## Slide 7: Our Approach and Methodology (2/2)
Implementation Support : We will undertake a detailed feasibility study, cost assessment as well support DPL in implementation of ERP
Feasibility Study
Identification of Critical Success Factors (CSFs) required for successful ERP Implementation and DPL’s readiness
Evaluation/assessment of change resistance and change management
Hardware and software support, networking etc.
Assessment of risk mitigation factors for key challenges and potential solutions
Cost Assessment
Based on the feasibility study outcomes, detailed assessment of costs will be carried out for:
Applications proposed to be implemented
IT infrastructure requirements in terms of Servers and support IT requirement, Data Center requirements, Networking requirement, Database requirement
Identification of costs incurred (Capex and Opex) for ERP implementation
Benefits assessment from ERP for DPL
Assessment of ERP Implementation in terms of Cloud vis-a-vis On-premise solution
Bidding and Implementation Support
Pre-Qualification requirements
Bid Evaluation criteria
Scope of Work and Terms of Reference
Post implementation arrangements
Performance standards

## Slide 8: Initial Study Work Plan (Week 1 – Week 7)
A structured approach to engaging key stakeholders across the organization based on a focused communication cadence, through local teams (for data collection) and use of various communication media to facilitate interactions
Update Calls / Discussion Meetings
Weeks
Kick off Meeting
Legend
Initiation
Stakeholder Interactions – As-Is Assessment
 | Deliverable
Shared to all within DPL | 
 | Stakeholder Meeting (one-on-one)
Attendees: Functional department teams, HOD, IT Team | 
 | Workshop
Attendees: DPL Leadership, project personnel, Project Core team | 
 | Working Team Meetings
Attendees: DPL project personnel, DI Team, Project Leadership (as required) | 
FRS
AS – IS Assessment And Roadmap Blueprint Documentation
Initiation
As-Is Process Understanding
1. As-Is Report (20 days)
4. Submission of RFP Document (45 days)
W1
W2
W3
W4
Design of roadmap blueprint document
3. Roadmap Blueprint Document (30 days)
Preparation of RFP for ERP Implementation
Subsequent activities as per the Scope of Work
W5
Preparation & Submission of RFP Document
RFP
W6
W7
Activities involving DPL Stakeholders

## Slide 9: Work Plan (Week 8 onwards)
A structured approach to engaging key stakeholders across the organization based on a focused communication cadence, through local teams (for data collection) and use of various communication media to facilitate interactions
Update Calls / Discussion Meetings
Months
Legend
Assistance in
Bid Evaluation
 | Deliverable
Shared to all within DPL | 
 | Stakeholder Meeting (one-on-one)
Attendees: Functional department teams, HOD, IT Team | 
 | Workshop
Attendees: DPL Leadership, project personnel, Project Core team | 
 | Working Team Meetings
Attendees: DPL project personnel, DI Team, Project Leadership (as required) | 
5. Kick off meeting for ERP Implementation (105 Days)
Activities involving DPL Stakeholders
4. Assistance in Bid Evaluation (90 Days)
M2
Evaluate As-Is document submitted by IA
M3
M4
M5
M6
M7
M8
M9
M10
M11
M12
Delivery milestones in assignment
6. Recommendation on approval of As-Is document for ERP Implementation (135 Days)
7. Recommendation on approval of System Design Document (SDD)(165 Days)
8. Pilot Roll Out & Change Management Workshop (210 Days)
Implementation Programme Management review and Recommendations
9. Go-Live of all modules (300 days)
11. Review of Post Go-Live scenario (365 Days)
 | Project Milestone
Project Milestone for Service Delivery | 
12. Post Go-live, first Financial Year closure & Financial Report generation
Share Progress Report and highlight issues fortnightly

## Slide 10: Roles and Responsibilities of SI, DPL and PMO
Coordination among the Project Stakeholders is a key requisite for success of the project
Aspect | Roles and Responsibility for System Integrator (SI) | Roles and Responsibility for PMO | Roles and Responsibility for DPL
Review of Project Plan from Time to Time | Adherence to Project Plan Highlight Timely Issues to the PMO and DPL | Timely review and reporting of project plans as well as deviation in the same to DPL and SI | Timely Assistance in resolving any operational challenges
Tracking and Review of all deliverables | Timely submission of all deliverables | Review of deliverables in a time bound manner as and when submitted by SI Coordination with DPL on the sign off for Deliverables in conjunction with SI | Review and sign off for the deliverables in a time bound manner
Review and reporting of all project related issues to DPL | Highlight Timely Issues to the PMO and DPL | Coordinate issue resolution with DPL and SI | Timely Assistance in resolving all issues
Implementation, Testing & Go Live | Time Bound Implementation for Testing & Go Live | Coordination between all stakeholders during implementation, testing and go-live | Sign off for Testing and Go Live

## Slide 11: Department Discussion Summary (1/3)
The departmental discussion has led to identifications of key challenges faced by them during day-to-day operations
Department | Summary of Discussion
Information technology | Various software’s are used based on Java and Oracle platform. Employee hardware grievance is handled offline and can be improved with the help of ERP system. Database is not maintained real time and should be integrated with ERP. License and water billing is done on FoxPro systems. Billing and accounting are not integrated and done manually. NIT software is used for procurement of materials. Payroll software looks after employee salary, income tax and reimbursement details Biometric systems in place for DPL admin employees and yet to be done for Power Plant Employees. Data from biometric is extracted and fed manually in the FoxPro System. No Database for storing the data from the software. Service request software is available but not utilized. Asset accounting done manually. No call centres for billing and payment related queries.
Stores and Purchase | Budget estimates are prepared every quarter and feedback from all departments are taken and made manually. Stores and Purchase (Technical) looks after Technical aspects like procurement of assets and coal, while Stores and Purchase (Corporate) looks after Stationary and small IT peripherals. Expenditure control is done at various levels by Standard Tendering Constitution Committee. All the departments send the data for procurement, then S&P initiates the tendering process . Payment and delivery are interlinked upon receipt of the goods from vendor. Data regarding procurement is updated manually. Inspection for obsolete asset is done by Audit team, if found obsolete then scrap valuation is done by Govt approved agency then auction is done. Payment of auctioned asset goes to Sr. Manager account. Approved vendor database not available. Data regarding work orders, vendors and its value is updated manually and are sent via E-mail to vendors. For goods <5Lacs E-procurement option is used and looked by IT team. Approvals are taken manually for procurement purposes.

## Slide 12: Department Discussion Summary (2/3)
The departmental discussion has led to identifications of key challenges faced by them during day-to-day operations
Department | Summary of Discussion
Human Resources | After the dissolution of WBSEDCL and WBSETCL , only employees of DPL Admin and power plant are considered. Number of employee ranges from 2100-2150. Attendance is recorded via bio-metric machines for Admin building and manually for power plant employees. While Bio-metric soon to be enabled for Power plant employees. Leave applications are submitted via hard copy to Admin Building. No process for automatic intimation of eligible employees for promotion after 7 years. Travel related queries are handled by IT team via FoxPro system. Employee database maintained manually. Advertisement for vacancies are rolled out bi-annually in case of urgent requirement of workforce and to be approved by Board of Directors. Appraisal system done in hard copy. Payroll and accounting is done in FoxPro system. MIS reports are rolled out manually. Transfer requests are carried out manually after approval from necessary heads.
Power Plant and maintenance | Generation forecasting done as per the previous year’s data . 1 year and 5 year Forecasting also done. All the maintenance data maintained manually. Intimation required from DPL 6 blocks(1.5Hr) before maintenance. Coal handling plant is responsible for both the quality and quantity checks of Coal. SOP’s are available for plant handling and maintenance activities. All the data is maintained in Excel file in which working hours of each asset is updated and one month prior, outage schedule is planned for replacement of the particular asset which is coming close to its life Staff is allocated manually at the time of maintenance, as per the designation, crew is allocated for tasks and for any other work, for which urgent workforce is required, it is arranged from outside for the duration of the maintenance. No process to track the status of maintenance task. Availability of inventory is done manually.

## Slide 13: Department Discussion Summary (3/3)
The departmental discussion has led to identifications of key challenges faced by them during day-to-day operations
Department | Summary of Discussion
Finance and Accounting | Budgets are prepared annually after input from all the departments for the next financial year . For OPEX budgets, MD approval is required and for CAPEX budgets, Board approval is required. Separate budgeting done for CAPEX and Revenue. No cash budgeting done. MIS is updated and rolled manually Payment vouchers are created and deductions to be checked before final billing of the vendor. Recording of the goods receipt note. Responsible for final payment after verification by user department. Accounting is done via goods receipt note which is updated in the FoxPro system. Advanced payment done to vendor after verification by user groups and process is same for CAPEX/OPEX projects but under different codes. No SOP’s available for the group. Monthly bank reconciliation report statements are maintained. Bank payment mode is RTGS Bank details of vendors maintained manually. Accounting for loan receipts and interest calculation for a bank is done manually. Debit and Credit notes are issued manually. Employee data is updated manually and sent to Bank for disbursement of salary , while accounting of salary done in FoxPro. Employee reimbursement process involves pre payment to employee and then bills are submitted to Salary section.
Coal Management | Accounting for coal requirement done as per generation data of previous year. Data forecasted for the next year beforehand. Coal is transported from CIL mines to DPL via Rail. Quality check of coal is done at both sending and receiving end by third party vendor. Coal requirement sent to CIL via railways software called Vice. Only tracking of status is available (Approved/Not approved). Final accounting done manually and ensured by Stores and Purchase team. No SOP for MIS reporting. Monthly invoice data is maintained manually. WhatsApp Group for data sharing and maintained manually.

## Slide 14: Key ERP Intervention Areas
Based on the discussions with various departments, we have identified a few immediate actionable areas where ERP can help improve the processes and drive efficiency for DPL
S. No. | Aspect | Area for Improvement
1 | Manual Record Keeping & Communication Mode | Most departments use email / excel sheets for communication & record keeping. A Document Management System with Communication tracker can assist in improving coordination
2 | Employee tagging and tracking | Employee data can be mapped in the system for time saving and for other activities like Leave requests, Reimbursements requests, PF and Salary/Promotion related data. This will help in case file database is lost or cannot be recovered.
3 | Procurement | Procurement process can be delayed due to manual approval process and paper trails. Paper trails can get lost and lead to redundancy as new requests are required in case of delays and change in vendor quotes due to inflation and other factors.
4 | Asset Tagging & Tracking | Asset tracking is done manually and leads to loss of time while checking assets individually via bin card through material codes.
5 | Equipment History & Maintenance Tracking | No formal IT based solution for tracking equipment history and maintenance plan. During the emergency situations, workforce allocation is done manually and required inventory is also tracked manually which takes a lot of time to do so.

## Slide 15: Next Steps
To expedite the seamless project study, we would need the support of DPL leadership, management and counterparts
Key requests
1
2
3
Counterpart Team and Nodal Person
Request to appoint a nodal person and counterpart team for each area for the project initiation, meeting set-up, making documents available and highlighting any project issues.
Stakeholder Meetings
Request to set-up 1-Day full meeting in person with each department. HoDs to direct team members for participation.
Data and Documents
Request to provide all the data and documents mentioned in the next slide.

## Slide 16: Data and Documents Required (Information Requirement List – 1)
  Power Plant O&M
  SOP’s for Plant maintenance and operation department along with PTW and other SOP’s if any.
  HR
  Organization structure along with processes of Reward and Recognition, Performance management and Learning and Development processes along with criteria.
  IT
  The list of software’s and initiatives taken till now. Also list of future initiatives taken for digitization of processes.
  Stores and Purchase
  As DLP follows the signed SOP’s for scrap disposal/auction . Same to be shared.
  Finance
  SOPs for Accounting Process as well as soft copy of annual accounts with tagged chart of accounts to be shared .
To better understand the working of different departments, we would need the support of DPL with the Required Data and Documents.

## Slide 17
Deloitte refers to one or more of Deloitte Touche Tohmatsu Limited, a UK private company limited by guarantee (“DTTL”), its network of member firms, and their related entities. DTTL and each of its member firms are legally separate and independent entities. DTTL (also referred to as “Deloitte Global”) does not provide services to clients. Please see www.deloitte.com/about for a more detailed description of DTTL and its member firms.
This material has been prepared by Deloitte Touche Tohmatsu India LLP (“DTTI LLP”), a member of Deloitte Touche Tohmatsu Limited, on a specific request from you and contains proprietary and confidential information. This material may contain information sourced from publicly available information or other third -party sources. DTTI LLP does not independently verify any such sources and is not responsible for any loss whatsoever caused due to reliance placed on information sourced from such sources. The information contained in this material is intended solely for you. Any disclosure, copying or further distribution of this material or its contents is strictly prohibited.
Nothing in this material creates any contractual relationship between DTT ILLP and you. Any mutually binding legal obligations or rights may only be created between you and DTTI LLP upon execution of a legally binding contract. By using this material and any information contained in it, the user accepts this entire notice and terms of use.
©2022 Deloitte Touche Tohmatsu India LLP. Member of Deloitte Touche Tohmatsu Limited
Deloitte Touche Tohmatsu India Private Limited (U74140MH199 5PTC093339), a private company limited by shares, was converted into Deloitte Touche Tohmatsu India LLP, a limited liability partnership (LLP Identification No. AAE-8458),with effect from October 1, 2015.

## Slide 18
ANNEXURE

## Slide 19: Identified List of Core & Subprocesses (1/3)
As part of structured approach, we look forward to discuss identified set of core and subprocesses for each module with concerned DPL stakeholders
Financial Accounting and Management
General Ledger/ Schedule
Manage Ledger Relationships
Manage Calendar
Manage Chart of Accounts
Manage GL Account Enquiry
Manage GL Master Data
Manage GL Transaction Posting
Manage Inter-office transactions
Manage Accounting Year-end Closing
Manage Consolidation
Manage Year-end Reporting
2. Accounts Receivable
Manage Integration with General Ledger
Manage Receivable Processing
Manage Incoming Payments
Manage Dishonoured Cheque Processing
Manage Collateral Deposit/Bank Guarantee
3. Accounts Payable
Manage Vendor Master Data
Manage Payable Processing
Manage Payment Processing
Manage Document Posting
Manage Vendor Account Enquiry
Manage Accounts Payable Reporting
4. Cash Management/ Treasury
General Function
Manage Cash Book
Manage Inter Unit Accounting
Manage Bank Reconciliation
Cash Management for Collection/Plant’s Accounts
Cash Management for Payment Accounts
Manage Cash Flow Forecast and Information Systems
Manage Loans and Deposit Management
Manage Inter-unit Transfer Details
Manage Cash Management/Treasury Reporting
5. Budgeting/Analysis
Manage Budget Preparation
Manage Revenue/ Operating expenditure budget
Manage Capital Expenditure Budget
Manage Budget Control
Manage Budgeting Reporting
6. Costing and Financial Control
Manage Cost Allocation - General Functions
Manage Costing Allocations
Manage Costing Analysis
Manage Activity Based Costing (ABC)
Manage Costing Enquiry/ Reporting
Manage Order and Project Management - General Functions
Manage Order and Project Management - Enquiry/ Reporting
Manage Profitability Analysis - General Functions
Manage Profitability Analysis – Planning
Manage Profitability Analysis - Enquiry/ Reporting
Manage Profit Centre Accounting – General Functions
Manage Profit Centre Accounting – Planning
Manage Profit Centre Accounting – Enquiry/ Reporting
7. Fixed Asset Accounting
Manage Fixed Asset Master Data maintenance
Manage Fixed Assets Register
Manage Assignment
Manage Addition of Fixed Assets
Manage Transfer/ Splitting of Fixed Assets
Manage Fixed Asset Disposal/ Retirement
Manage Depreciation of Fixed Assets
Manage Insurance of Fixed Assets
Manage Revaluation of Fixed Assets
Manage Physical Inventory of Fixed asset
ILLUSTRATIVE

## Slide 20: Identified List of Core & Subprocesses (2/3)
As part of structured approach, we look forward to discuss identified set of core and subprocesses for each module with concerned DPL stakeholders
Financial Accounting and Management
Fuel Accounting
Way-bill management
Medical Advance/Other Allowances
Financial/MIS Reporting Requirements
Reporting Requirements for Estimates of Financial Resources
Reporting Requirements for Annual Financial Statement (Previous Year - Actual, Current Year - Budgeted and Ensuring Year - Estimates)
Reporting Requirements for Revenue Monitoring
Other Reporting Requirements
Organization Management
Human Resource Policies, Rules and Regulations
Policies for Contractual and Outsourced employees
Contract Labor Management
Employee Master (Employee Service Book)
House Building Loan
Employee Self Service (ESS)
Employee Details
Attendance & Leave Management
Manpower Planning, Recruitment & Selection
Compensation & Benefits
Training
Performance Appraisal System
E-Exit (Full and Final Settlement)
Transfers & Promotions
Organization Policies & Procedures
Voluntary Retirement Scheme (VRS)
General HR & Administration Processes
Time and Leave Management
ILLUSTRATIVE
9. Payroll
Payroll Management
Support for allowances, reimbursements, loans etc.
Personal Taxation
Deductions
Pay slip Run
PF & Terminal Benefit Management
Gratuity Management
Pension Management
Deputation
10. Employee Status Change
Transfers (Deputation/Job Rotation)
Promotions
Training
Compensation & Benefits
Performance Appraisal
Succession Planning
Staffing
Manpower Planning
Recruitment
Selection
Hiring
Confirmation
Human Resource Management

## Slide 21: Identified List of Core & Subprocesses (3/3)
As part of structured approach, we look forward to discuss identified set of core and subprocesses for each module with concerned DPL stakeholders
Human Resource Management
Grievance Redressal
Legal
Occupational Health
HR&A Dashboard
Administration
Travel Management
E-Payment
Guest House Room Booking
Quarter Allotment
Procurement and issuance of medicines
Employee Welfare and CSR
Performance Linked Incentive Scheme
E - Exit (Full and Final Settlement)
Plant Maintenance
General
Breakdown Maintenance
Preventive Maintenance
Engineering Declaration
Unit Overhauling
2. Asset Management
General
Maintain Asset and its Performance
Manage Bill of Material (BoM) / Tools / Spares
Cost Control of Assets
Capex & Non-Capex work
3. Operation Performance Management
General
ORT Meeting
Energy Audit
MoU with Power Plants
Availability Declaration
Trip Analysis
4. O&M Budgeting
General
5. Billing and Payment
Bill verification for payment
Integration with Third Party applications
1. Inventory Management
Material Records Management (Material Master)
Manage Inventory
Material Requirements Planning
Goods Receipt
Goods Issue
Inter-Store/plant stock Transfer
Store Return
Material Disposal
Physical Inventory Verification
Integration with Third Party applications
2. Procurement
Vendor Records Management
Procurement Planning
Purchase Requisition
RFQ/ Tendering
Purchase Order Management
Turnkey Procurement
Service Procurement
Contract Management
Plant Operation & Maintenance Management
ILLUSTRATIVE
Material Management

## Slide 22: Detailed Scope of Work (1/4)
We understand that the objective of this assignment is to assist DPL in identifying business requirements, assessing feasibility of ERP implementation with a roadmap
As-is Study /Assessment
Assessment of Processes and Organization
Study of existing business processes / procedures within the organizational functions under consideration for implementation of ERP
Study of existing Chart of Accounts (COA) and Cost Centers and review its suitability vis-a-vis the proposed ERP adoption. The study will also recommend necessary modifications if required.
Study of organizational hierarchy, departments, roles and responsibilities of various personnel.
Study of available manpower, and competency and skill-levels for adoption of ERP.
Study of existing information management practices, including information security practices.
Study of organization readiness, at all levels of the organization, to adopt ERP.
Study of real-time operational Data capture in DCS, non-DCS & ABT systems and recommend procedure to integrate them with ERP system
Assessment of Existing IT infrastructure
Study of existing IT infrastructure (including communication network) and applications used by DPL across various locations.
Study of IT infrastructure and application management practices, including IT security measures deployed.
Study of user familiarity, expertise and satisfaction in using such infrastructure and applications.
Study of existing IT human resources and recommend necessary additions during and post ERP implementation scenario.

## Slide 23: Detailed Scope of Work (2/4)
We understand that the objective of this assignment is to assist DPL in identifying business requirements, assessing feasibility of ERP implementation with a roadmap
Preparation of Road Map Blueprint for ERP Implementation
To-be Design with the following objectives:
Meet DPL’s business specific requirements.
Meet DPL’s requirement to establish best-of-breed processes through deployment of ERP.
Meet DPL’s requirement to establish best-deployment of ERP.
Implementing leading standards in technology design and power sector domain best-practices, addressing the need for scalability and flexibility without undermining the data integrity and transparency required for enabling the processes.
Solution design for ERP implementation:
Based on the assessment made during the as-is study, propose various ERP modules with a consideration of the above-mentioned objectives
Develop the Functional Requirement Specifications for modules required by DPL for implementation of ERP.
Look into the readiness of integration of the existing DCS & NON-DCS system with the proposed ERP solution. Recommend additions to be done by DPL and as well as by the ERP implementer to achieve the intended integration
Discuss and finalize PP implementation and finalize the scope and coverage of the ERP.
Discuss and recommend various procurement details related to ERP
Consider DPL’s ongoing and future business requirements and legacy IT infrastructure and application systems while designing the solution.
Consider business continuity aspects of DPL while designing the solution with training and change management requirements associated with the ERP implementation while developing the implementation roadmap.

## Slide 24: Detailed Scope of Work (3/4)
We understand that the objective of this assignment is to assist DPL in identifying business requirements, assessing feasibility of ERP implementation with a roadmap
Preparation of Road Map Blueprint for ERP Implementation
Design of IT Infrastructure
Discuss and finalize the IT infrastructure (hardware, software, network, facility) required for implementation of the ERP, based on the implementation option selected by DPL and finalize the IT architecture for ERP implementation at DPL.
Evaluate the reusability of the existing IT hardware infrastructure, to optimize the procurement cost.
Advise on the retirement and integration requirements of some of the legacy and existing applications, if required, for successful implementation of ERP.
Adopt latest technology standards and practices while developing the IT infrastructure. Undertake due care and caution to ensure that the IT architecture and its constituents are scalable to take care of future IT requirements of DPL.
Suggest the measures to ensure business continuity considering single-point-of- failures and disaster recovery scenarios.
Preparation of TT budget
Based on the IT architecture agreed for the implementation of ERP, prepare a detailed budget highlighting the capital expenditure and the operational expenditure requirements.
Assist DPL in the preparation of such explanation notes, as may be required for justification of the proposed budget, for administrative approval.

## Slide 25: Detailed Scope of Work (4/4)
We understand that the objective of this assignment is to assist DPL in identifying business requirements, assessing feasibility of ERP implementation with a roadmap
Selection of ERP Implementation Agency
Based on the requirement of goods and services for ERP implementation at DPL, assist DPL in the preparation of a Request for proposal (RFP) document for the procurement, implementation and management of the ERP solution, and for the selection of a qualified and capable Implementation Agency (IA).
Prepare bid documents for ERP solution & Implementation Agency (IA).
Assist in bid process management, including evaluation of technical and financial proposals, assistance in discussions with bidders for Implementation Agency, preparation of corrigendum, and preparation of final evaluation report, and assistance in contract finalization with implementation agency
Program Management of ERP Implementation
Assist DPL in Program Management of the ERP solution implementation for the duration of the Pilot go-live as well as for the roll-out to all project locations.
Co-ordinate with various stakeholders (DPL, ERP Implementing Agency, and. other IT vendors, if any) and assist in key decision making and review of the work being undertaken during implementation and rollout.
Review the project plan agreed with the Implementation Agency from time during the implementation.
Coordinate between DPL and the Implementation Agency staff on meetings related to solution configuration, testing and other implementation related tasks.
Track and review of all deliverables submitted by the Implementation Agency to DPL.
Review and report all project related issues to DPL
Review all project management and change management actions, including training of users across various locations of DPL.
Analyze and recommend DPL on of release of payment to Implementation Agency as per terms of the ERP Order.