## Slide 1
Selection of Transaction Advisor for Assessment of Institutional Development and Human Resource Management of The Durgapur Projects Limited (DPL)
RFQ NO: WBDPL/PUR/CORP/RFQ/110/2021-2022
The Durgapur Projects Limited
Kick-off Presentation
September 08, 2022
© Deloitte Touche Tohmatsu India LLP

## Slide 2
COVERAGE
 | Project Context Our understanding of the project
 | Scope of Work Summary of the Scope and Key Deliverables
 | Our Approach and Methodology Structured Approach and Methodology to meet targets
 | Work Plan Summarized Activities and Delivery Timelines
 | Next Steps Way Forward
1
2
3
4
5

## Slide 3: Project Context
Proper organization structure with effective manpower planning plays a vital role in successful operation of businesses
Our Understanding of current dynamics
Need of an enhanced Performance Management System in line with DPL’s Vision and Strategy with formulation of organizational and departmental KPIs
Review of existing key employee policies, incentive schemes and employee Training plans to keep them at par with other utilities and state guidelines
Review of current manpower planning at DPL to ensure optimal manpower distribution among business avenues to meet organization capacity addition strategy
Need of a redeployment plan for DPL’s existing manpower deployed in a) hived-off businesses (Coke Oven) and b) possible hived off business ventures (Water Works, Central Workshop)
DPL is looking to enter Green Energy business streams and new technology initiatives like Renewable Energy, Electric Vehicles and Green Hydrogen which eventually require re-alignment in current organization structure and capacity building
Analysis of DPL’s current outsourcing models with their effectiveness and impact on manpower optimization followed by exploration of other outsourcing models for other business services
(i) Review of organization Structure (ii) Review of Manpower Planning (iii) Enhanced Performance Management System (iv) Review of KPI’s at organization and department Level (v) Review of Outsourcing Deployment Models
It is in this context that DPL looks forward to

## Slide 4: Summary of Scope of Work
To assist DPL with effective organization structure, manpower planning, training and capacity building plan
  Note - Detailed Scope of Work to be followed as per the tender document throughout the course of assignment (attached in Annexure)
Study and Recommendations - Human Resource & Organizational Aspects
PHASE 01
SUB-COMPONENT 1 - Review of Organization Structure, and manpower and recommended changes
  Review of Organization structure across all levels, identification of gaps in alignment to strategy/business plan and processes
  Reviewing roles & responsibilities and accountability matrix at various critical levels in the organization
  Assessing the manpower (on-roll and sanctioned strength) across all levels in organization, both at corporate level and Plant
  Recommend standard outsourcing models
  Develop the Performance Management System in line with the Company Vision and Strategy
  Evaluate current incentive schemes in place and assess the feasible incentive scheme mechanism design
  Review ERP or IT software implementations and integrations between HR and PMS modules and identify improvement areas
SUB-COMPONENT 2 - Training and Capacity Building
  Conduct skill gap assessment study and identify focus areas
  Study the training policy and programs of DPL including assessing the effectiveness of the training
  Benchmark the training and capacity building needs with similar best performing organizations in Power Sector within India
  Identify future capacity building gaps and develop a revised Training Strategy, Plan and calendar for DPL
  Recommend training and capacity building institutional set up
  Devise institutional mechanism for Training effectiveness and KPIs for the training function
01
PHASE 02
02
Implementation Support

## Slide 5: Key Focus Areas
Key focus areas for assessment to attain maximum value addition
Review of Organization Structure
Manpower Planning
Performance Management System
Review of KPI’s at organization and department Level
Review of Outsourcing Deployment Models

## Slide 6: Our Approach and Methodology
Deloitte will utilize its rich industry knowledge and prior experience of working with DPL (through ongoing ERP implementation engagement) to develop the best solutions to achieve desired results.
We will undertake a detailed study of DPL’s current organization structure, manpower planning, PMS and KPIs
Understand Business practices and Management Expectations
Discussion with DPL Top Management on Team Formation and Communication Protocols
Discussion on way forward of Project Plan
Conduct interviews with DPL stakeholders from concerned departments
Review roles and responsibilities with accountability matrix
Assess actual and required manpower
Collect and review available manuals and HR policies
Conduct skill gap assessment
Collation and consolidation of documentation/ inputs received from discussions
Development and finalization of As-Is assessment
Development and finalization of As-Is Training Policy
Identify the areas of improvements
Incorporate proposed changes in the existing HR policies
Redesign training policies for maximum value additions
Review of KPI’s at organization and department Level
Design capacity building Plan
Preparation of finalized To-Be and redesigned training policy
Updation of organization and department level HR manuals
Preparation of final report
Implementation Support
STAGE A
STAGE B
STAGE C
STAGE D
STAGE E

## Slide 7: Phase 1 Work Plan (Week 01 – Week 12)
Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Update Calls / Discussion Meetings
Weeks
Kick off Meeting
Stakeholder Interactions
 | Deliverable
Shared to all within DPL | 
 | Stakeholder Meeting (one-on-one)
Attendees: Concerned department teams, HODs, Nodal Team | 
 | Workshop
Attendees: DPL Leadership, project personnel, Project Core team | 
 | Working Team Meetings
Attendees: DPL project personnel, Deloitte Team, Project Leadership | 
Presentation
AS – IS Assessment
Initiation
Inception Report (Week 1)
Presentation on As – Is Assessment and Training Policy & Plan
4. Report on Capacity Building Plan including revised KPIs & MIS (Week 12)
To-Be Assessment, Redesigned Training Policy and Plan
TO-BE Assessment, Capacity Building Plan & Recommendations
Activities involving DPL Stakeholders
A structured approach to engaging key stakeholders across the organization to achieve desired results
Legend
2. As-Is Assessment, As-Is Training Policy & Plan (Week 4)
3. Human Resource and Organization To-Be Report & Redesigned Training Policy and Plan (Week 8)
Capacity Building Plan
Preparation of Manual & Final Report
5. Updated manuals and Final Report (Week 12)
  Festive Weeks: Week 5 - Week 8 (including holidays on account of festivals such as Durga-puja, Dusshera and Diwali.)
Final Presentation
As-Is Assessment and Training Policy Plan Understanding & Presentation

## Slide 8: Key Deliverables
Our approach on submission of key deliverables
Key Deliverables as per RFP | Key Deliverables as per RFP
 | Inception Report
 | As-Is Assessment on structure, manpower etc.
 | As-Is Training Policy and Plan
 | Report & presentation on To – be and recommendations
 | Report & presentation on the Redesigned Training Policy & Plan
 | Report & Presentation on Capacity Building Plan including revised KPIs & MIS
 | Updated manuals and Final Report submission
A
B
C
D
E
Deloitte’s Deliverable Submission Approach | Deloitte’s Deliverable Submission Approach | Timelines
 | Inception Report | Week 1
 | As-Is Assessment, As-Is Training Policy & Plan | Week 4
 | Human Resource and Organization To-Be Report & Redesigned Training Policy and Plan | Week 8
 | Report on Capacity Building Plan including revised KPIs & MIS | Week 12
 | Updated manuals and Final Report submission | Week 12
A
B
C
D
F
G
E

## Slide 9: Next Steps
Key requests from Deloitte
Way forward to ensure seamless execution
Request to appoint a nodal person and counterpart team for each area, making documents available and highlighting any project issues.
Counterpart Team and Nodal Person
Request to set-up in person meetings with each department. HoDs to direct team members for participation.
Stakeholder Meetings
Request to provide timely feedback and sign off for our deliverables
Timely Review and Feedback
Request to provide all the data and documents required for assessment. Preliminary data requirement covered in upcoming slide
Data and Documents

## Slide 10: Preliminary Data Requirement for Assessment
Organization Structure | Actual Workforce as of August 2022 Any revisions in sanctioned workforce numbers? Any plans on organization restructuring
Roles & Responsibilities and Accountability Matrix | Details of Job Description / Roles & Responsibilities laid down for each department Which stakeholders are involved in preparation of R&R? Formation of RACI/Accountability matrix?
Employee Compensation Policy | Details of latest employee compensation policy Details of last revisions made in compensation policy Differences in compensation for on-roll vs off-roll employees
Details of key tasks/activities per department | List of key activities executed by department Methodology to estimate task completion time? Methodology to allocate optimal work distribution
Outsourcing Models | Details of activities in a department which are currently outsourced? Monitoring and evaluation of outsourced tasks? (Report generation / cross verification) Compensation estimation for outsourced activities
Employee Policies | Employee Policies Book Details of last revisions made
Incentives Schemes | Details of incentives schemes (both at department and individual level) Are there different incentive schemes for on-roll vs off-roll employee?
Rewards & Recognition | Details of Rewards and Recognition ( Monetary vs non-monetary) Criteria for Rewards and Recognition nomination and selection
PMS & Organization / Department Level KPIs | Identification of KPIs along with setting of target values for monitoring Monitoring frequency Details on performance feedback system to employees and linkage between the performance evaluation and compensation package
  Note – A detailed questionnaire with data collection format will be shared separately with DPL Management

## Slide 11
Deloitte refers to one or more of Deloitte Touche Tohmatsu Limited, a UK private company limited by guarantee (“DTTL”), its network of member firms, and their related entities. DTTL and each of its member firms are legally separate and independent entities. DTTL (also referred to as “Deloitte Global”) does not provide services to clients. Please see www.deloitte.com/about for a more detailed description of DTTL and its member firms.
This material has been prepared by Deloitte Touche Tohmatsu India LLP (“DTTI LLP”), a member of Deloitte Touche Tohmatsu Limited, on a specific request from you and contains proprietary and confidential information. This material may contain information sourced from publicly available information or other third -party sources. DTTI LLP does not independently verify any such sources and is not responsible for any loss whatsoever caused due to reliance placed on information sourced from such sources. The information contained in this material is intended solely for you. Any disclosure, copying or further distribution of this material or its contents is strictly prohibited.
Nothing in this material creates any contractual relationship between DTT ILLP and you. Any mutually binding legal obligations or rights may only be created between you and DTTI LLP upon execution of a legally binding contract. By using this material and any information contained in it, the user accepts this entire notice and terms of use.
©2022 Deloitte Touche Tohmatsu India LLP. Member of Deloitte Touche Tohmatsu Limited
Deloitte Touche Tohmatsu India Private Limited (U74140MH199 5PTC093339), a private company limited by shares, was converted into Deloitte Touche Tohmatsu India LLP, a limited liability partnership (LLP Identification No. AAE-8458),with effect from October 1, 2015.

## Slide 12
ANNEXURE

## Slide 13: Detailed Scope of Work – Phase 1 (1/2)
Sub-component 1: Review of Organization Structure, and manpower and recommended changes
Review of Organization structure (both at Corporate and Plant) across all the levels including the senior management, identification of gaps in alignment to the strategy / business plan and processes in the organization and recommendations for adjustments in the organization structure, in particular to meet the new challenges of future asset development, diversification of asset base from conventional to renewable and green energy, EVs, new business ventures and related diversification plans, backward linkages in coal supply chain via captive mining and moving to digital operations.
Reviewing roles & responsibilities and accountability matrix at various critical levels in the organization. Also understand the time spent on various tasks by each category of employees.
Assessing the manpower (on-roll and sanctioned strength) across all levels (Group I, II, III and IV) in the organization, both at corporate level and Plant and identification of key challenges with respect to the same. Such analysis would include benchmarking of manpower with other utilities (at least 2 well performing public utilities similar or larger in terms of geographical area and business operations similar to DPL, 2 private Indian generation utilities (Stand alone / integrated).
Review employee compensation policy compared to state pay matrix and other state-owned co’s’.
Creation of Employee Handbook covering all the above rules and policies including all the various emoluments / entitlements of the employees to be made.
Study the existing manpower deployed in Power Plant, Water Works, Central Workshop and Coke Oven divisions and assist in preparing a redeployment plan for DPL.
Recommend standard outsourcing models (with details of procurement strategy, SLAs, bidding parameters, key procurement term sheet etc.) for at least 4 types of major services based on current HR practice. Any 4 major services in HR can be chosen for the same. For example, Hospital/Medical Services, Idle Manpower deployment, House-keeping Services, Revenue generations etc.
Develop the Performance Management System in line with the Company Vision and Strategy including but not limited to the formulation of organizational KPIs, identification of measurable Key Result Areas and the corresponding measures / Performance Indicators (functional KPIs), definition of departmental targets for those measures, introduction of individual performance evaluation framework based on organizational and functional KPIs, performance feedback system to employees and linkage between the performance evaluation and compensation package.
Analyze DPL’s outsourcing models (including comparison with models employed by other utilities with due care to adapt to the variations with respect to the demography, geography etc.). Assess effectiveness of the currently deployed models and conduct an impact evaluation on manpower optimization resulting from outsourcing.

## Slide 14: Detailed Scope of Work – Phase 1 (2/2)
Sub-component 1: Review of Organization Structure, and manpower and recommended changes
Undertake a review of the key employee policies and suggest changes for encouraging accountability and rewards.
Support in approval process for the changes across organization structure, employee policies, outsourcing models etc. (including presentation to the BOD, if required by DPL management)
Evaluate current incentive schemes in place and assess the feasible incentive scheme mechanism design for DPL including its rollout plan and implementation model
While conducting the above analysis, it is expected that the consultant shall visit, at least three power plants across varying age and two captive mining operations and the HQ to understand DPL’s operations and roles and responsibilities of the employees.
Review the existing ERP or IT software implementations and integrations, if any, between HR and PMS modules and identify improvement areas (Presently there is no ERP System in DPL. However, ERP Implementation is under process).
Sub-component 2: Training and Capacity building
Conduct a skill gap assessment study for DPL and identify the key areas where focus needs to be accorded
Study the training policy and programs of DPL including assessing the effectiveness of the training
Benchmark the training and capacity building needs with similar best performing organizations in Power Sector within India.
Based on the Sector Targets and Business Plan of DPL, identify future capacity building gaps and develop a revised Training Strategy, Plan and calendar for DPL (including recommendation of tie up with national and international institutes).
Recommend the training and capacity building institutional set up. The verticals, funding, scope for the set up. Identify how the Training function can also generate revenues including a transition plan to be a Profit Centre from current cost center model.
Devise an institutional mechanism for Training effectiveness and KPIs for the Training function.