## Slide 1: Institutional Strengthening Project : Implementations of Revenue Management System (RMS) at Nepal Electricity Authority (NEA)
Monthly Status Update MM YYYY

## Slide 2
Overall Status | Scope | Timeline | Budget
On-Track
At-Risk
Off track/ Requires Escalation or Re-planning
RMS Implementation : Program Status Report (As of MM/YY)
Key Risks and Mitigation Steps
Risk | Impact | Status | Owner | Date Raised | Mitigation Steps/Recommendation
Delay in FRS signature | Delay in FRS signature would lead to cascading effect in overall project timeline | Open | M/s LongShine (SI) | 20th May 2023 | 1. 2. 3.
Program Milestones1
Executive Summary
Nepal Electricity Authority (NEA) had signed an agreement with M/s LongShine on 9th January 2023 for implementing RMS for consumers of Nepal
The total period of the contract is 6.5 years (1.5 Year of implementation period and Facility Management Services (FMS) support for 5 Years)
The project kick-off happened on 10th March 2023 and M/s. LongShine had commenced their work on 12th March 2023
Next 4 Week Milestones
Mar 23 | Apr 23 | May 23 | Jun 23 | July 23 | Aug 23 | Sep 23 | Oct 23 | Nov 23 | Dec 23 | Jan 24 | Feb 24 | Mar 24 | Apr 24 | May 24 | Jun 24 | Jul 24 | Aug 24
# | Milestone | Target Date | Status
1 | FRS Signature | 15 May 23 | 
2 | Hardware arrival | 15 Aug 23 | 
3 |  |  | 
4 |  |  | 
5 |  |  | 
6 |  |  | 
Program Sponsor | Asian Development Bank | Program Budget | $ 9.867 Million
Project Director | Chandha Neupane (NEA) | Duration of Project | 6.5 years (1.5 year implementation)
Supplier/ System Integrator | M/S. LongShine | PMO Support | Deloitte Touche Tohmatsu India LLP
Current Accomplishments
Project Initiation documents (FRS, To-be, As-Is,etc) submitted by M/S LongShine
In-person meeting conducted between M/s LongShine, NEA and Deloitte on observations of the submitted documents
Next Steps to Address Off Track Milestones
Milestone #: <Insert Activity Here>
Next Steps to Address At Risk Milestones
Milestone #: <Insert Activity Here>
FRS signature
Hardware Arrival
Data Digitization completion
Hardware SAT
CCC Acceptance
Pilot BCT & Cut-over Go-live
DR UAT
Training &
Data completion
BCT & Enterprise wide roll out
Project Completion
Project
Kick-off
1 The Project milestones shown are in accordance with the Kick-off deck presented by M/s LongShine on 10th March 2023
We are here

## Slide 3
On-Track
At-Risk
Off track/ Requires Escalation or Re-planning
RMS Implementation : Detailed Report (As of MM/YY)
Activities/ Tasks | Activities/ Tasks |  | Target date | Responsibility | Status | Remarks
 | Milestone-1: |  |  |  |  | 
 |  |  |  |  | Completed | 
 |  |  |  |  | Completed | 
 |  |  |  |  | In Progress | 
 |  |  |  |  | Yet to start | 
 |  |  |  |  | Delayed | 
 | Milestone-2 : |  |  |  |  | 
Illustrative

## Slide 4
RMS Implementation : Detailed Risk and Mitigation plan
Risk ID | Risk | Risk Level | Impact | Status | Owner | Date Raised | Mitigation Steps
Major concern. The Risk requires immediate, active intervention
Minor concern. One or two tasks in plan affected and remedial action is required
Normal concern. Risk or Issue is being actively managed, and no additional attention needed
Legend
Illustrative

## Slide 5
RMS Implementation : Open and Close Actions
Action ID | Action | Owner | Date Raised | Due Date | Status | Remarks
Illustrative

## Slide 6
Deloitte refers to one or more of Deloitte Touche Tohmatsu Limited, a UK private company limited by guarantee (“DTTL”), its network of member firms, and their related entities. DTTL and each of its member firms are legally separate and independent entities. DTTL (also referred to as “Deloitte Global”) does not provide services to clients. Please see www.deloitte.com/about for a more detailed description of DTTL and its member firms.
This material has been prepared by Deloitte Touche Tohmatsu India LLP (“DTTILLP”), a member of Deloitte Touche Tohmatsu Limited, on a specific request from you and contains proprietary and confidential information. This material may contain information sourced from publicly available information or other third-party sources. DTTILLP does not independently verify any such sources and is not responsible for any loss whatsoever caused due to reliance placed on information sourced from such sources. The information contained in this material is intended solely for you. Any disclosure, copying or further distribution of this material or its contents is strictly prohibited.
Nothing in this material creates any contractual relationship between DTTILLP and you. Any mutually binding legal obligationsorrights may only be created between you and DTTILLP upon execution of a legally binding contract. By using this material and any information contained in it, the user accepts this entire notice and terms of use.
©2023 Deloitte Touche Tohmatsu India LLP. Member of Deloitte Touche Tohmatsu Limited
Deloitte Touche Tohmatsu India Private Limited (U74140MH199 5PTC093339), a private company limited by shares, was converted into Deloitte Touche Tohmatsu India LLP, a limited liability partnership (LLP Identification No. AAE-8458),with effect from October 1, 2015.