## Slide 1
NTPC Strategy 2025 : Project Kickoff
NTPC Limited
July 20th, 2020
© 2020. For information, contact Deloitte Touche Tohmatsu India LLP
Draft for discussion

## Slide 2: Our team today….
To be updated later
WIP

## Slide 3: Agenda
 | Context Setting and Programme Objectives
 | Approach for the Engagement
 | Work plan and key milestones
 | Key asks from NTPC
1
2
3
4

## Slide 4: Context setting and objectives
Context
Meeting Objectives
  Objective of today’s meeting are to discuss:
    The expectations and focus areas from NTPC for strategy 2025 initiative
    Our Proposed approach for the 12-week journey along different workstreams and identification of quick win opportunities
    Timelines for the key milestones across diagnostic, solutioning and roadmap phases
    Support required from NTPC for the engagement
  NTPC has engaged Deloitte to help develop it strategy roadmap for 2025
  With the impact of COVID, the ways in which NTPC operates, especially with regard to people, process and technology has been drastically altered
  The current challenges will required an organization-wide transformation encompassing business functions, organizational structure and setup, existing and emerging business areas to prepare NTPC on its growth path for the short and medium term
  Hence, there is a need to strengthen NTPC’s 2025 strategy with a comprehensive review of its business and operating model with a strong focus on maintaining resilience and agility
WIP

## Slide 5: Agenda
 | Context Setting and Programme Objectives
 | Approach for the Engagement
 | Work plan
 | Key asks from NTPC
1
2
3
4

## Slide 6: Our approach towards “Strategy 2025”
We will take a work-stream approach to develop the short and medium term strategy
Business function transformation
HR transformation
New and emerging areas
O&M and Fuel Management
W1
W2
W3
W4
Basis our last few discussions, we plan to divide the entire assignment into four (4) distinct work-streams…
Prioritized business functions, such as
Procurement,
Inventory management,
Project planning, execution & monitoring,
Business development
Quality control & inspections…
Focus areas
Talent management
  Recruitment process (virtual/ digitally enabled)
  Onboarding of employees (virtual/ digitally enabled)
  Succession Management Framework
Framework for identification of specialist roles
Diversification and business adjacencies, such as
Renewable (RE)
Consultancy
Distribution
EV infrastructure
Trading
International foray etc.
Core business areas
Fleet level O&M
Regulatory strategy & policy advocacy
Digitalization
Short & Medium term fuel security
WIP
Saurabh to modify HR workstream as per discussion on call <SD> Modified

## Slide 7: Work stream – W1: Business function transformation, W4:O&M and Fuel Management
  Assessment of 3-4 key business processes and functional structure. We propose:
    Procurement & Contract management
    Project planning, execution & monitoring
    Quality control & inspections
    Business development
  Understand current performances, challenges, KPIs
  Identify boundary conditions for existing processes
  Impact assessment of Covid-19 in current processes
Diagnostic phase
Week 1 to 4
Deep dive on improvement areas
Bring ‘outside in’ industry perspective for benchmarking, advise on ‘new normal’
Define the future state recommendations along people, process and technology, basis agility, cost and efficiency
Develop hypothesis and prioritize those among ‘Quick win’ and ‘Medium term’ interventions - select the medium term interventions basis complexity, urgency and investment requirement
Develop high level business case if required
Finalize and agree on the interventions
Solutioning phase
Week 4 to 8
  Develop implementation roadmap with definite timeframe
  Identify and recommend resources and capabilities required
    Enhancement of existing capabilities
    Development of new capabilities
Roadmap and Implementation plan
Week 8 to 12
  Diagnostic report
Report on short term action agenda e.g. change in operating model, process interventions, digitalization pilot etc.
Report on medium term action agenda e.g. digitalization of O&M fleet, strengthening project monitoring cell etc.
Implementation roadmap with capability enhancement plan
Key
Deliverables
Key Activities
Methodology
Interview with Business Process Owner – ED/Director
Small group workshop – GMs and EDs (1 – 2 Nos)
Secondary research
Focused Group Discussion with business process owner/functional head and leadership team for validating recommendations (1 – 2 Nos)
Leveraging Deloitte collaterals on best practices
Deloitte prioritization and business case framework
Focused Group Discussion with business process owner/functional head and leadership team for validating recommendations
(Short & Medium term)

## Slide 8: Work stream – W2: HR transformation
WIP
  Assessment of 3-4 key HR priority areas
    Talent management
  Recruitment process (virtual/ digitally enabled)
  Onboarding of employees (virtual/ digitally enabled)
  Succession Management Framework
  Framework for identification of specialist roles
  Understand current processes and challenges
  Understand future expansion plans of NTPC and impact of those in HR management
  Impact assessment of Covid-19 in current HR processes; define the ‘new normal’
Diagnostic phase
Week 1 to 4
Deep dive on improvement areas
Bring ‘outside in’ industry perspective for benchmarking current HR processes
Conduct High Impact HR Maturity Assessment
Define the future state recommendations in line with best practices
Develop hypothesis and prioritize those among ‘Quick win’ and ‘Medium term’ interventions
Finalize and agree on the interventions
Solutioning phase
Week 4 to 8
  Develop implementation roadmap with definite timeframe
  Identify and recommend resources and capabilities required
    Enhancement of existing capabilities
    Development of new capabilities
Roadmap and Implementation plan
Week 8 to 12
  Diagnostic report
Report on short term action agenda e.g. creation of new roles, virtual recruitment, skill development etc.
Report on medium term action agenda e.g. creation of a CoE
Implementation roadmap with capability enhancement plan
Key
Deliverables
Key Activities
Methodology
Interview with HR Director and ED
Small group workshop – GMs and EDs (1 – 2 Nos)
Interview with process owners
FGDs with a few employee personas (2-3)
Focused Group Discussion with functional head and leadership team for validating recommendations (1 – 2 Nos)
Leveraging Deloitte collaterals on best practices
High Impact HR Maturity Assessment Framework
Focused Group Discussion with functional head and leadership team for validating recommendations
(Short & Medium term)

## Slide 9: Work stream – W3: New and emerging business areas
  Assess Indian power sector outlook till 2025
    Demand-supply, technology landscape, capacity addition
  Assess evolving Govt. policies & regulations
  Understand leadership priorities and views on Potential opportunities & possible areas of expansion for NTPC
  Identify new areas with business potential (3 – 4 areas), such as
    Renewables, Consultancy, Distribution, Trading
Diagnostic phase
Week 1 to 4
Detail out of each business option and ops model change, basis
  Market attractiveness
  Skill gap analysis
  Risk return analysis
  Business case
Identifying ‘Quick win’ interventions
Detail out medium term strategic choices and complex interventions, like alliance, technology investment etc.
Highlight risk factors and mitigation steps
Finalize and agree on the interventions
Solutioning phase
Week 4 to 8
  Develop implementation roadmap with definite timeframe
  Identify and recommend resources and capabilities required
    Enhancement of existing capabilities
    Development of new capabilities
Roadmap and Implementation plan
Week 8 to 12
  Diagnostic report
Report on short term action agenda
Report on medium term action agenda
Implementation roadmap with capability enhancement plan for new business areas
Key
Deliverables
Key Activities
Methodology
Interview with leadership/ Business Unit owners – ED/Director
Small group workshop – GMs and EDs (1 – 2 Nos) for ideation in each area
Secondary research
Focused Group Discussion with business unit owner and leadership team for validating recommendations (1 – 2 Nos)
Deloitte ‘Strategic Choice Cascade’
Deloitte prioritization and business case framework
Focused Group Discussion with business unit owner and leadership team for validating recommendations
(Short & Medium term)

## Slide 10: Agenda
 | Context Setting and Programme Objectives
 | Approach for the Engagement
 | Work plan
 | Key asks from NTPC
1
2
3
4

## Slide 11: Proposed project Work plan
Key Activities | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Diagnostic phase (Week 1-4) |  |  |  |  |  |  |  |  |  |  |  | 
Kickoff meeting and stakeholder alignment |  |  |  |  |  |  |  |  |  |  |  | 
Study of NTPC’s business processes and functional structure |  |  |  |  |  |  |  |  |  |  |  | 
Study of global & Indian power/ energy sector outlook – Demand & Supply, Energy Basket(Gas, Solar, Storage etc.), Consumer Segment, Financial Health, etc., in a medium-term horizon including near term scenarios |  |  |  |  |  |  |  |  |  |  |  | 
Study of impact of Government interventions in terms of policies, regulations, acts and economic stimulus |  |  |  |  |  |  |  |  |  |  |  | 
Impact of COVID-19 on business continuity and growth challenges, before the Sector and NTPC |  |  |  |  |  |  |  |  |  |  |  | 
Diagnostic presentation |  |  |  |  |  |  |  |  |  |  |  | 
Solutioning phase (Week 4-8) |  |  |  |  |  |  |  |  |  |  |  | 
Evaluate and longlist strategic options for short and medium term |  |  |  |  |  |  |  |  |  |  |  | 
Focused group discussion with functional head and leadership team for validating recommendations |  |  |  |  |  |  |  |  |  |  |  | 
Prioritization of strategic option and preparation of and business case |  |  |  |  |  |  |  |  |  |  |  | 
Develop value proposition & define target customer segments for new business |  |  |  |  |  |  |  |  |  |  |  | 
Design target operating model for initiatives to be rolled out |  |  |  |  |  |  |  |  |  |  |  | 
Interim presentation on short term action agenda (one – two year timeline) and medium term action agenda (Till 2025) |  |  |  |  |  |  |  |  |  |  |  | 
Roadmap and Implementation plan (Week 8-12) |  |  |  |  |  |  |  |  |  |  |  | 
Prepare roadmap and define governance framework for implementation |  |  |  |  |  |  |  |  |  |  |  | 
Prepare detailed implementation charter |  |  |  |  |  |  |  |  |  |  |  | 
Align organization structure as per target operating model |  |  |  |  |  |  |  |  |  |  |  | 
Setup continuous monitoring of implementation plan |  |  |  |  |  |  |  |  |  |  |  | 
Final report submission and closure workshop |  |  |  |  |  |  |  |  |  |  |  | 
Workshop
Deliverable
Weeks
We are here today
Diagnostic report presentation by end of 4th week
Interim reports on short term and medium term action plan
Final Presentation Report presentation and closure
Presentation to CMD/Directors
Work-streams
Business function transformation
HR transformation
New and emerging areas
O&M and Fuel Management

## Slide 12: Stakeholder interaction plan
..
WIP
Himadri to add
<SD> added some data requirements
Process and Policy documents for Recruiment, Onboarding and Succession Management
Number of hires per month / annum broken by type (lateral, campus, other channels)
Framework for identification of specialist roles
Reports and dashboards for recruitment, onboarding and succession management

## Slide 13: Agenda
 | Context Setting and Programme Objectives
 | Approach for the Engagement
 | Work plan
 | Key asks from NTPC
1
2
3
4

## Slide 14: Key asks – What we need from NTPC
Participation of NTPC leadership in key workshops and meetings
Key sessions will be designed in workshop formats. Success of these sessions is hinged on active participation from key members. For each of the phases such as :
  Diagnostic /As –is assessment
  Strategic option prioritization
Designated SPOCs (for each of the four work streams)
We will work closely with personnel of NTPC for each work stream. SPOCs for each are to be selected and we expect to work closely with them throughout the engagement and expect support in sharing data and information as and when required to facilitate progress
Periodic review by leadership/ business heads
Periodic review by leadership and business heads is critical for the success of this assignment. A governance framework would be developed and agreed upon – it should be adhered to the entire team so that the engagement is successful
Logistics for any on-site visits
If we need to visit specific plant sites or locations as mutually agreed upon, NTPC will help facilitate such site visits
External stakeholder interaction
NTPC will help in arranging meeting/interaction with various external stakeholders (if required)
We are partners on this journey and expect to follow a collaborative approach
Information request
NTPC will provide the required information/data for the diagnostic assessment. Information request templates will be provided after the Kick-off

## Slide 15
Deloitte refers to one or more of Deloitte Touche Tohmatsu Limited, a UK private company limited by guarantee (“DTTL”), its network of member firms, and their related entities. DTTL and each of its member firms are legally separate and independent entities. DTTL (also referred to as “Deloitte Global”) does not provide services to clients. Please see www.deloitte.com/about for a more detailed description of DTTL and its member firms.
This material has been prepared by Deloitte Touche Tohmatsu India LLP (“DTTILLP”), a member of Deloitte Touche Tohmatsu Limited, on a specific request from you and contains proprietary and confidential information. This material may contain information sourced from publicly available information or other third party sources. DTTILLP does not independently verify any such sources and is not responsible for any loss whatsoever caused due to reliance placed on information sourced from such sources. The information contained in this material is intended solely for you. Any disclosure, copying or further distribution of this material or its contents is strictly prohibited.
Nothing in this material creates any contractual relationship between DTTILLP and you. Any mutually binding legal obligationsorrights may only be created between you and DTTILLP upon execution of a legally binding contract. By using this material and any information contained in it, the user accepts this entire notice and terms of use.
©2019 Deloitte Touche Tohmatsu India LLP. Member of Deloitte Touche Tohmatsu Limited
Deloitte Touche Tohmatsu India Private Limited (U74140MH199 5PTC093339), a private company limited by shares, was converted into Deloitte Touche Tohmatsu India LLP, a limited liability partnership (LLP Identification No. AAE-8458),with effect from October 1, 2015.